## St4
|  | Shift Start | 5:05 | [10 empty] | Cristy Miller
|  | Break Start Time | 8:50 | [10 empty] | Tony Chupp
|  | Break End Time | 9:05 | [10 empty] | Gary Schabach
|  | Shift End | 13:05 | [10 empty] | Leon Schwartz
|  | Start Time | 2016-11-16 08:30 | [10 empty] | Braydon Martin
End Time
|  | Number of People | 10
|  | TAKT | 1.55 |  |  |  | DAYS
|  | Minutes Per Person Per Takt | 697.5 |  |  |  | min
|  | Minutes per TAKT (7.5 hr day) | 6975 |  |  |  | min
|  | Available Production Minutes | 7207.5
|  | Minutes per TAKT (Working Time) | 720.75 |  |  |  | 72.075
|  | Predicted Schedule Time | 6043.5 |  |  |  | 604.35
|  | Available Time | 1164
Comments / Issues
Station | Process_# | Process_Name | Task Time | Clock Time | # People | Responsible | 8.5x24 | 206129 |  | Heath Hawkins |  |  |  | Leon Hochstetler |  |  |  | Brian Miller |  |  |  | Rob Smith |  |  |  | Mike Hochstetler |  |  |  | JR Wood |  |  |  |  | Tanner Swihart |  |  |  | Steve Rodman |  |  |  | Nate Turner |  |  |  | Rex Wert
5 | 5060 | Ramp Door Install | 30 | 15 | 2 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3646 | 15 | 705.75 | 1 | 42690.3646 | 15 | 705.75
5 | 5080 | License Plate | 2 | 2 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.366 | 17 | 703.75 |  | 42690.3646 | 15 | 705.75
5 | 5090 | Grab Handles (Ramp) | 10 | 10 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3729 | 27 | 693.75 |  | 42690.3646 | 15 | 705.75
5 | 5100 | "Fire Ext. | 15 | 15 | 1 | 15 |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3729 | 27 | 693.75 | 1 | 42690.375 | 30 | 690.75
5 | 5110 | Clean Exterior | 35 | 35 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3729 | 27 | 693.75 | 1 | 42690.3993 | 65 | 655.75
5 | 5120 | Exterior Stickers and Logos | 20 | 20 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3868 | 47 | 673.75 |  | 42690.3993 | 65 | 655.75
5 | 5130 | Caulk Exterior | 45 | 45 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3868 | 47 | 673.75 | 1 | 42690.4306 | 110 | 610.75
5 | 5140 | Clean Interior | 80 | 80 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3868 | 47 | 673.75 | 1 | 42690.4861 | 190 | 530.75
5 | 5150 | Clean Interior - Cabinets CS Front | 5 | 5 | 1 | [5 empty] | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3868 | 47 | 673.75 | 1 | 42690.4896 | 195 | 525.75
5 | 5230 | Clean Interior - Happijac - Rear | 5 | 5 | 1 | [5 empty] | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3868 | 47 | 673.75 | 1 | 42690.4931 | 200 | 520.75
5 | 5260 | Clean Interior - Sofa - CS - Rear | 5 | 5 | 1 | [5 empty] | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3868 | 47 | 673.75 | 1 | 42690.4965 | 205 | 515.75
5 | 5280 | Clean Interior - Sofa - RS - Rear | 5 | 5 | 1 | [5 empty] | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3868 | 47 | 673.75 | 1 | 42690.5 | 210 | 510.75
5 | 5340 | Insulation - floor | 10 | 10 | 1 | [5 empty] | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3868 | 47 | 673.75 | 1 | 42690.5069 | 220 | 500.75
5 | 5350 | Interior Stickers | 11 | 11 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3868 | 47 | 673.75 | 1 | 42690.5146 | 231 | 489.75
5 | 5360 | Caulk Interior | 70 | 70 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3868 | 47 | 673.75 | 1 | 5:31 | 301 | 419.75
5 | 5370 | Shower Curtain | 5 | 5 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3868 | 47 | 673.75 | 1 | 5:36 | 306 | 414.75
5 | 5380 | Grease Caps | 2 | 2 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3882 | 49 | 671.75 |  | 5:36 | 306 | 414.75
5 | 5390 | Tighten Wheel Lugs & check air presure in tires | 5 | 5 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3917 | 54 | 666.75 |  | 5:36 | 306 | 414.75
5 | 5400 | Install Graphics | 130 | 130 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4819 | 184 | 536.75 |  | 5:36 | 306 | 414.75
5 | 5440 | Tie Down Rings | 2 | 2 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.4819 | 184 | 536.75 | 1 | 5:38 | 308 | 412.75
5 | 5450 | Hi-Pot Test | 10 | 10 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4889 | 194 | 526.75 |  | 5:38 | 308 | 412.75
5 | 5460 | Electrical Systems check | 45 | 45 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.5201 | 239 | 481.75 |  | 5:38 | 308 | 412.75
5 | 5470 | Functionallity Test | 20 | 20 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.534 | 259 | 461.75 |  | 5:38 | 308 | 412.75
5 | 5510 | Functionallity Test - Happijac - Rear | 5 | 5 | 1 | [5 empty] | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.5375 | 264 | 456.75 |  | 5:38 | 308 | 412.75
5 | 5540 | Functionallity Test - Sofa - CS - Rear | 5 | 5 | 1 | [5 empty] | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.541 | 269 | 451.75 |  | 5:38 | 308 | 412.75
5 | 5560 | Functionallity Test - Sofa - RS - Rear | 5 | 5 | 1 | [5 empty] | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.5444 | 274 | 446.75 |  | 5:38 | 308 | 412.75
5 | 5650 | Functionallity Test - Stereo | 5 | 5 | 1 | [5 empty] | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 5:09 | 279 | 441.75 |  | 5:38 | 308 | 412.75
5 | 5710 | Inspection / Walk Through | 30 | 30 | 0 | [5 empty] | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 5:09 | 279 | 441.75 |  | 5:38 | 308 | 412.75
5 | 5720 | Standard Rework | 30 | 30 | 1 |  | 647 | 0.89768 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
Station | Process_# |  |  | 0 | 0 |  | 7.0x20 | 206173 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
4 | 4010 | Finish Water Heater | 10 | 10 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3611 | 10 | 710.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
4 | 4020 | Outside Water Fill | 6 | 6 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3653 | 16 | 704.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
4 | 4030 | Install Outside Shower | 5 | 5 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3687 | 21 | 699.75 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
4 | 4040 | LP Tray and Tanks | 7 | 7 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 42690.3542 | 0 | 720.75 | 1 | 42690.359 | 7 | 713.75 |  | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
4 | 4050 | install intellipower | 120 | 120 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  | 1 | 42690.4375 | 120 | 600.75 |  | 42690.359 | 7 | 713.75 |  | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
4 | 4060 | install battery disconnect & divider panal | 20 | 20 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  | 1 | 42690.4514 | 140 | 580.75 |  | 42690.359 | 7 | 713.75 |  | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
3 | 4080 | Interior Hook Up | 120 | 120 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  | 1 | 42690.5347 | 260 | 460.75 |  | 42690.359 | 7 | 713.75 |  | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
4 | 4110 | Install LP Lines | 30 | 30 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 42690.5347 | 260 | 460.75 | 1 | 42690.3799 | 37 | 683.75 |  | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
4 | 4120 | Main Switch Panel Hook Up No Stereo 45 | 45 | 45 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  | 1 | 5:35 | 305 | 415.75 |  | 42690.3799 | 37 | 683.75 |  | 5:39 | 309 | 411.75 |  | 5:38 | 308 | 412.75
4 | 4150 | Fenders - 7 Wide | 15 | 15 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 5:35 | 305 | 415.75 |  | 42690.3799 | 37 | 683.75 | 1 | 5:54 | 324 | 396.75 |  | 5:38 | 308 | 412.75
4 | 4160 | Lower Rub Rail | 40 | 40 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 5:35 | 305 | 415.75 |  | 42690.3799 | 37 | 683.75 | 1 | 6:34 | 364 | 356.75 |  | 5:38 | 308 | 412.75
4 | 4180 | Wire Lower Clearance Lights | 15 | 15 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 5:35 | 305 | 415.75 |  | 42690.3799 | 37 | 683.75 | 1 | 6:49 | 379 | 341.75 |  | 5:38 | 308 | 412.75
4 | 4190 | Fender Lights - 7.0 Wide | 30 | 30 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 5:35 | 305 | 415.75 |  | 42690.3799 | 37 | 683.75 | 1 | 7:19 | 409 | 311.75 |  | 5:38 | 308 | 412.75
4 | 4200 | Flow Through Vents | 20 | 20 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 5:35 | 305 | 415.75 |  | 42690.3799 | 37 | 683.75 | 1 | 7:39 | 429 | 291.75 |  | 5:38 | 308 | 412.75
4 | 4220 | Install Motorbase | 15 | 15 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  | 1 | 5:50 | 320 | 400.75 |  | 42690.3799 | 37 | 683.75 |  | 7:39 | 429 | 291.75 |  | 5:38 | 308 | 412.75
4 | 4240 | Install Outside Coax | 15 | 15 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  | 1 | 6:05 | 335 | 385.75 |  | 42690.3799 | 37 | 683.75 |  | 7:39 | 429 | 291.75 |  | 5:38 | 308 | 412.75
4 | 4260 | Exterior Recept Install | 15 | 15 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  | 1 | 6:20 | 350 | 370.75 |  | 42690.3799 | 37 | 683.75 |  | 7:39 | 429 | 291.75 |  | 5:38 | 308 | 412.75
4 | 4280 | Exterior 12V Outlet | 10 | 10 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  | 1 | 6:30 | 360 | 360.75 |  | 42690.3799 | 37 | 683.75 |  | 7:39 | 429 | 291.75 |  | 5:38 | 308 | 412.75
4 | 4300 | Install Kitchen Overhead | 17 | 17 | 0 | JW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 | Move to 3 |  | 6:30 | 360 | 360.75 |  | 42690.3799 | 37 | 683.75 |  | 7:39 | 429 | 291.75 |  | 5:38 | 308 | 412.75
4 | 4310 | Set Refer | 30 | 30 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 6:30 | 360 | 360.75 | 1 | 42690.4007 | 67 | 653.75 |  | 7:39 | 429 | 291.75 |  | 5:38 | 308 | 412.75
4 | 4320 | Tail Lights - License Plate Light Installed | 60 | 60 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 6:30 | 360 | 360.75 |  | 42690.4007 | 67 | 653.75 | 1 | 8:39 | 489 | 231.75 |  | 5:38 | 308 | 412.75
4 | 4340 | Refer Hook Up | 14 | 14 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 6:30 | 360 | 360.75 | 1 | 42690.4104 | 81 | 639.75 |  | 8:39 | 489 | 231.75 |  | 5:38 | 308 | 412.75
4 | 4350 | Outside Refer Vent | 5 | 5 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3687 | 21 | 699.75 |  |  | 6:30 | 360 | 360.75 | 1 | 42690.4139 | 86 | 634.75 |  | 8:39 | 489 | 231.75 |  | 5:38 | 308 | 412.75
4 | 4360 | Outside Water Heater and Furnace Vent | 15 | 15 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3792 | 36 | 684.75 |  |  | 6:30 | 360 | 360.75 |  | 42690.4139 | 86 | 634.75 |  | 8:39 | 489 | 231.75 |  | 5:38 | 308 | 412.75
4 | 4380 | Install Outside Water Heater Door | 5 | 5 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3826 | 41 | 679.75 |  |  | 6:30 | 360 | 360.75 |  | 42690.4139 | 86 | 634.75 |  | 8:39 | 489 | 231.75 |  | 5:38 | 308 | 412.75
4 | 4390 | wire upper clearance lights | 35 | 35 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  | 1 | 7:05 | 395 | 325.75 |  | 42690.4139 | 86 | 634.75 |  | 8:39 | 489 | 231.75 |  | 5:38 | 308 | 412.75
4 | 4410 | Trim Ramp Door Opening | 20 | 20 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:05 | 395 | 325.75 |  | 42690.4139 | 86 | 634.75 | 1 | 8:59 | 509 | 211.75 |  | 5:38 | 308 | 412.75
4 | 4420 | Install Windows (All Std) | 30 | 30 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:05 | 395 | 325.75 |  | 42690.4139 | 86 | 634.75 |  | 8:59 | 509 | 211.75 | 1 | 6:08 | 338 | 382.75
4 | 4450 | Day and Night Shades | 20 | 20 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:05 | 395 | 325.75 |  | 42690.4139 | 86 | 634.75 |  | 8:59 | 509 | 211.75 | 1 | 6:28 | 358 | 362.75
4 | 4460 | ATP Kickplate | 45 | 45 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:05 | 395 | 325.75 |  | 42690.4139 | 86 | 634.75 |  | 8:59 | 509 | 211.75 | 1 | 7:13 | 403 | 317.75
4 | 4470 | Hook Up A/C (1st) | 31 | 31 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  | 1 | 7:36 | 426 | 294.75 |  | 42690.4139 | 86 | 634.75 |  | 8:59 | 509 | 211.75 |  | 7:13 | 403 | 317.75
4 | 4490 | Cove | 120 | 120 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:36 | 426 | 294.75 | 1 | 42690.4972 | 206 | 514.75 |  | 8:59 | 509 | 211.75 |  | 7:13 | 403 | 317.75
4 | 4500 | Trim Interior | 60 | 60 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:36 | 426 | 294.75 |  | 42690.4972 | 206 | 514.75 | 1 | 9:59 | 569 | 151.75 |  | 7:13 | 403 | 317.75
4 | 4520 | Vents Garnish - Roof | 5 | 5 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  | 1 | 7:41 | 431 | 289.75 |  | 42690.4972 | 206 | 514.75 |  | 9:59 | 569 | 151.75 |  | 7:13 | 403 | 317.75
4 | 4580 | Towel Bar | 8 | 8 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 42690.4972 | 206 | 514.75 |  | 9:59 | 569 | 151.75 | 1 | 7:21 | 411 | 309.75
4 | 4590 | Install Mirror | 5 | 5 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 42690.4972 | 206 | 514.75 |  | 9:59 | 569 | 151.75 | 1 | 7:26 | 416 | 304.75
4 | 4600 | Shower Curtain Rod | 5 | 5 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 42690.4972 | 206 | 514.75 |  | 9:59 | 569 | 151.75 | 1 | 7:31 | 421 | 299.75
4 | 4610 | Install Toilet | 7 | 7 | 0 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 | Move to 3 |  | 7:41 | 431 | 289.75 |  | 42690.4972 | 206 | 514.75 |  | 9:59 | 569 | 151.75 |  | 7:31 | 421 | 299.75
4 | 4620 | LP Test - Water Test | 25 | 25 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 | 1 | 42690.5146 | 231 | 489.75 |  | 9:59 | 569 | 151.75 |  | 7:31 | 421 | 299.75
4 | 4650 | Install Entrance Door | 7 | 7 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.359 | 0 | 713.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 42690.5146 | 231 | 489.75 |  | 9:59 | 569 | 151.75 |  | 7:31 | 421 | 299.75
4 | 4670 | Grab Handle Entrance Door | 5 | 5 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.359 | 0 | 713.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 42690.5146 | 231 | 489.75 |  | 9:59 | 569 | 151.75 | 1 | 7:36 | 426 | 294.75
4 | 4680 | Trim Entrance Door | 20 | 20 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.359 | 0 | 713.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 | 1 | 42690.5285 | 251 | 469.75 |  | 9:59 | 569 | 151.75 |  | 7:36 | 426 | 294.75
4 | 4690 | Refer Panels | 5 | 5 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.359 | 0 | 713.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 | 1 | 42690.5319 | 256 | 464.75 |  | 9:59 | 569 | 151.75 |  | 7:36 | 426 | 294.75
4 | 4700 | Awning cradle | 5 | 5 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3625 | 0 | 708.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 42690.5319 | 256 | 464.75 |  | 9:59 | 569 | 151.75 |  | 7:36 | 426 | 294.75
4 | 4710 | Awning | 30 | 30 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3833 | 0 | 678.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 42690.5319 | 256 | 464.75 |  | 9:59 | 569 | 151.75 |  | 7:36 | 426 | 294.75
4 | 4720 | Front Baggage Door | 10 | 10 | 1 | NT |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 42690.5319 | 256 | 464.75 | 1 | 10:09 | 579 | 141.75 |  | 7:36 | 426 | 294.75
4 | 4730 | Bathdoor | 10 | 10 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 42690.5319 | 256 | 464.75 | 1 | 10:19 | 589 | 131.75 |  | 7:36 | 426 | 294.75
4 | 4740 | Trim Bathroom Door | 15 | 15 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 42690.5319 | 256 | 464.75 | 1 | 10:34 | 604 | 116.75 |  | 7:36 | 426 | 294.75
4 | 4780 | Prep Bed Door - RS | 33 | 33 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 | 1 | 5:19 | 289 | 431.75 |  | 10:34 | 604 | 116.75 |  | 7:36 | 426 | 294.75
4 | 4800 | Install Bed Door - RS | 217 | 217 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 | 1 | 8:56 | 506 | 214.75 |  | 10:34 | 604 | 116.75 |  | 7:36 | 426 | 294.75
4 | 4880 | Install Dinette CS - Rear | 45 | 45 | 1 | RW |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 8:56 | 506 | 214.75 |  | 10:34 | 604 | 116.75 | 1 | 8:21 | 471 | 249.75
4 | 4920 | Flood Test | 80 | 80 | 1 | SR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 | 1 | 10:16 | 586 | 134.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
4 | 4970 | install & hook up LP tanks | 15 | 15 | 1 | SR | 1597 | 2.2157 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 | 1 | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
Station | Process_# |  |  | 0 | 0 |  | 7.0x20 | 206112 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.3826 | 41 | 679.75 |  |  | 7:41 | 431 | 289.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3010 | install bathroom upper cab. & countertop | 37 | 37 | 1 | J.R. |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.4083 | 78 | 642.75 |  |  | 7:41 | 431 | 289.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3020 | install bath backsplash | 8 | 8 | 1 | J.R. |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.4139 | 86 | 634.75 |  |  | 7:41 | 431 | 289.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3030 | set linen in bathroom | 48 | 48 | 1 | J.R. |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.4472 | 134 | 586.75 |  |  | 7:41 | 431 | 289.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3040 | set kitchen broom closet | 50 | 50 | 1 | J.R. |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.4819 | 184 | 536.75 |  |  | 7:41 | 431 | 289.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3050 | install bargman cord & junction box | 65 | 65 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.4819 | 184 | 536.75 |  | 1 | 8:46 | 496 | 224.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3060 | wire electric jack | 10 | 10 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.4819 | 184 | 536.75 |  | 1 | 8:56 | 506 | 214.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3070 | Install Battery | 20 | 20 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.4819 | 184 | 536.75 |  | 1 | 9:16 | 526 | 194.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3100 | Loom Wires Where Needed | 27 | 27 | 1 | TS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 |  | 42690.4819 | 184 | 536.75 |  | 1 | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3110 | Low point drains & water lines. (std. unit) | 26 | 26 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.5 | 210 | 510.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3120 | Install Shower | 8 | 8 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.5056 | 218 | 502.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3130 | Shower Faucet | 2 | 2 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.5069 | 220 | 500.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3140 | Set Bath Wall and Drill Holes for Plumbing and Wiring | 20 | 20 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.5208 | 240 | 480.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3150 | Plumb Drain Vents | 10 | 10 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.5278 | 250 | 470.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3160 | Panel Interior Bathroom | 10 | 10 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.5347 | 260 | 460.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3170 | Panel Outside of Bath Wall | 9 | 9 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3833 | 0 | 678.75 | 1 | 42690.541 | 269 | 451.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3180 | Install remainder of ceiling panals | 30 | 15 | 2 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3937 | 0 | 663.75 | 1 | 5:14 | 284 | 436.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3190 | Panel All Interior Walls | 120 | 120 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3937 | 0 | 663.75 | 1 | 7:14 | 404 | 316.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3210 | Install and Hook Up Front Plumbing Kit | 13 | 13 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3937 | 0 | 663.75 | 1 | 7:27 | 417 | 303.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3220 | Mount pump & hook up electric | 5 | 5 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3937 | 0 | 663.75 | 1 | 7:32 | 422 | 298.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3230 | Install LP Lines | 20 | 20 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3937 | 0 | 663.75 | 1 | 7:52 | 442 | 278.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3240 | Set Furnace and Install Furnace Vent | 20 | 20 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3937 | 0 | 663.75 | 1 | 8:12 | 462 | 258.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3250 | Refer Cabinet | 9 | 9 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3937 | 0 | 663.75 | 1 | 8:21 | 471 | 249.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3260 | Trim Refer Cabinet | 10 | 10 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3937 | 0 | 663.75 | 1 | 8:31 | 481 | 239.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3270 | Finish installing shower (rivets) & shower head with accesseries | 18 | 18 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3937 | 0 | 663.75 | 1 | 8:49 | 499 | 221.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3300 | Drill External Speaker Holes | 10 | 10 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4007 | 0 | 653.75 |  | 8:49 | 499 | 221.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3310 | Install Water Heater | 10 | 10 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.4007 | 0 | 653.75 | 1 | 8:59 | 509 | 211.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3320 | Install Plumbing and Vent Pipes | 20 | 20 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.4007 | 0 | 653.75 | 1 | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3330 |  |  |  |  | RS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.4007 | 0 | 653.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3340 |  |  |  |  | RS |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.4007 | 0 | 653.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3360 | Hang Rear Corners Stainless Steel | 8 | 8 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4062 | 0 | 645.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3370 | Prep for CS Metal | 15 | 15 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4167 | 0 | 630.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3380 | Degabond CS | 5 | 5 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4201 | 0 | 625.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3390 | Hang CS Metal | 25 | 25 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4375 | 0 | 600.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3420 | Route CS Metal | 10 | 10 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4444 | 0 | 590.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3430 | Prep for RS Metal | 1 | 1 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4451 | 0 | 589.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3440 | Degabond RS | 5 | 5 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4486 | 0 | 584.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3450 | Hang RS Metal | 25 | 25 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.466 | 0 | 559.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3480 | Route RS Metal | 10 | 10 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4729 | 0 | 549.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3510 | Prep Front End Metal | 5 | 5 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4764 | 0 | 544.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3520 | Metal Front End | 25 | 25 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4937 | 0 | 519.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3530 | Gravel Guard | 20 | 20 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.5076 | 0 | 499.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3540 | Front Trim Pieces | 15 | 15 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.5181 | 0 | 484.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3550 | Route Baggage Doors | 5 | 5 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.5215 | 0 | 479.75 |  | 9:19 | 529 | 191.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3560 | Set Furnace and Install Furnace Vent | 17 | 17 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.5215 | 0 | 479.75 | 1 | 9:36 | 546 | 174.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3570 | Set Kitchen Base | 7 | 7 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.5215 | 0 | 479.75 | 1 | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3580 | Insulate Roof | 28 | 28 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.541 | 0 | 451.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3590 | Metal Roof and Degabond | 21 | 21 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 5:20 | 0 | 430.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3600 | Bend Down Edge of Metal Roof | 10 | 10 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 5:30 | 0 | 420.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3610 | Intall Front Roof Trim Piece | 10 | 10 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 5:40 | 0 | 410.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3620 | Upper Rub Rail | 45 | 45 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 6:25 | 0 | 365.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3630 | Awning Rail | 10 | 10 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 6:35 | 0 | 355.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3640 | Upper Clearance Lights | 15 | 15 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 6:50 | 0 | 340.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3660 | Holes for Plumbing Vents | 6 | 6 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 6:56 | 0 | 334.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3670 | Route Roof Vents | 5 | 5 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:01 | 0 | 329.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3690 | Install Vents and Seal MaxAir Brackets | 15 | 15 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:16 | 0 | 314.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3710 | Install Plumbing and Vent Covers and Tail Pipes | 15 | 15 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:31 | 0 | 299.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3750 | Clean Roof | 6 | 6 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:37 | 0 | 293.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3760 | Seal Roof | 20 | 20 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:57 | 0 | 273.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3770 | Seal Under Front Radius and Down Front Edge | 18 | 18 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 8:15 | 0 | 255.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3780 | Refer Vent Cap | 2 | 2 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 8:17 | 0 | 253.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3800 | Upper Flow Thru Vent - Scene Light - Speakers | 35 | 35 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 8:52 | 0 | 218.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3810 | Seal Under Rub Rail | 20 | 20 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 9:12 | 0 | 198.75 |  | 9:43 | 553 | 167.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3820 | Kitchen Plumbing | 20 | 20 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 9:12 | 0 | 198.75 | 1 | 10:03 | 573 | 147.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3830 | Install Kitchen Counter Top | 9 | 9 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 9:12 | 0 | 198.75 | 1 | 10:12 | 582 | 138.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3840 | install kitchen backsplash | 8 | 8 | 1 | JR |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 9:12 | 0 | 198.75 | 1 | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3850 | Wire Upper Cleanance and Loading Lights (Int. Hook Up) | 50 | 50 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 10:02 | 0 | 148.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3880 | Flow Through Vents | 20 | 20 | 1 | MH |  |  |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
3 | 3900 |  |  |  | 0 |  | 1221 | 1.6941 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
Station | Process_# |  |  | 0 | 0 |  | 8.5x28FB | 206511 |  |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2010 | Top weld and axles | 40 | 20 | 2 | Tator |  |  |  | 1 | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3681 | 20 | 700.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2020 | Install Coupler | 15 | 15 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3785 | 35 | 685.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2030 | Install D-Rings | 52 | 52 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4146 | 87 | 633.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2050 | cut first piece of flooring (7' wide) |  |  | 0 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.4146 | 87 | 633.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2060 | Level Frame | 5 | 5 | 1 | BM |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3576 | 0 | 715.75 |  | 42690.4146 | 87 | 633.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2070 | Grind Top Welds | 20 | 20 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.3576 | 0 | 715.75 | 1 | 42690.4285 | 107 | 613.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2080 | Set Wheel wells or Wheel Well Metal | 5 | 5 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.3611 | 0 | 710.75 |  | 42690.4285 | 107 | 613.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2090 | Install flooring ( 2 people) | 160 | 80 | 2 | BM |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4167 | 0 | 630.75 | 1 | 42690.484 | 187 | 533.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2120 | Drill Plumbing Holes and Toilet Drains | 12 | 12 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.425 | 0 | 618.75 |  | 42690.484 | 187 | 533.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2130 | Drill Holes for Gas Lines and Low Points | 10 | 10 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4319 | 0 | 608.75 |  | 42690.484 | 187 | 533.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2140 | install 3 inch grommmets for holes | 10 | 10 | 1 | BM |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4389 | 0 | 598.75 |  | 42690.484 | 187 | 533.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2150 | mark wall lines on floor/cover floor | 40 | 40 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4667 | 0 | 558.75 |  | 42690.484 | 187 | 533.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2160 | cover floor | 20 | 20 | 1 | BM |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.4806 | 0 | 538.75 |  | 42690.484 | 187 | 533.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2170 | Set Walls - Rear Header - Front Walls | 30 | 15 | 2 | LS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.491 | 0 | 523.75 | 1 | 42690.4944 | 202 | 518.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2180 | Set and Weld Roof | 45 | 22.5 | 2 | LS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.5062 | 0 | 501.25 | 1 | 42690.5097 | 224.5 | 496.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2190 | Final Weld on Sidewalls | 50 | 50 | 1 | LS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.5062 | 0 | 501.25 | 1 | 42690.5444 | 274.5 | 446.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2200 | final weld on front walls | 20 | 20 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.5062 | 0 | 501.25 | 1 | 5:24 | 294.5 | 426.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2210 | Drill Holes for Wiring | 40 | 40 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.5062 | 0 | 501.25 | 1 | 6:04 | 334.5 | 386.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2220 | Grommet All Holes Where Needed | 10 | 10 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 42690.5062 | 0 | 501.25 | 1 | 6:14 | 344.5 | 376.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2600 | Install Ground Wires | 10 | 10 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 42690.5132 | 0 | 491.25 |  | 6:14 | 344.5 | 376.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2230 | Rough Wire Unit (Front Bedroom: 4.5 hrs) | 150 | 150 | 1 | BM |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 6:49 | 0 | 341.25 |  | 6:14 | 344.5 | 376.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2300 | Dinette RS - Rear | 1 | 1 | 1 | [5 empty] | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 6:50 | 0 | 340.25 |  | 6:14 | 344.5 | 376.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2320 | A/C - 1st | 8 | 8 | 1 | [5 empty] | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 6:58 | 0 | 332.25 |  | 6:14 | 344.5 | 376.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2410 | Loading Lights | 3.5 | 3.5 | 1 | [5 empty] | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:01 | 0 | 328.75 |  | 6:14 | 344.5 | 376.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2450 | Grind Sidewalls | 35 | 35 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 7:01 | 0 | 328.75 | 1 | 6:49 | 379.5 | 341.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2460 | Square Front and Rear Ends | 10 | 10 | 1 | LS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:11 | 0 | 318.75 |  | 6:49 | 379.5 | 341.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2470 | Cut Out Flooring for Doorway | 10 | 10 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 7:11 | 0 | 318.75 | 1 | 6:59 | 389.5 | 331.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2480 | Caulk Floor Around Outside Edge | 5 | 5 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 7:11 | 0 | 318.75 | 1 | 7:04 | 394.5 | 326.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2490 | Radius Blocks in Window Corners | 10 | 10 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 7:11 | 0 | 318.75 | 1 | 7:14 | 404.5 | 316.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2520 | Azdel Front End | 30 | 30 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 7:11 | 0 | 318.75 | 1 | 7:44 | 434.5 | 286.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2530 | Set Interior Front Wall and Cage | 25 | 12.5 | 2 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:23 | 0 | 306.25 | 1 | 7:56 | 447 | 273.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2540 | Water Shelf |  |  | 0 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 7:23 | 0 | 306.25 |  | 7:56 | 447 | 273.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2550 | Water Heater Hookup |  |  | 0 | BM |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 7:23 | 0 | 306.25 |  | 7:56 | 447 | 273.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2560 | Undercoat Wheel Well | 5 | 5 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 7:23 | 0 | 306.25 | 1 | 8:01 | 452 | 268.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2570 | Paint at Openings (Windows - etc) | 5 | 5 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 7:23 | 0 | 306.25 | 1 | 8:06 | 457 | 263.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2580 | VBH on End Tubes and at Wheels | 10 | 10 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:33 | 0 | 296.25 |  | 8:06 | 457 | 263.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2590 | install /remove scaffold | 10 | 10 | 1 | [5 empty] | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:43 | 0 | 286.25 |  | 8:06 | 457 | 263.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2610 | Azdel Inside Front Wall | 15 | 15 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 7:58 | 0 | 271.25 |  | 8:06 | 457 | 263.75 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2620 | Install 1st Piece of Azdel On Each Side of Sidewall | 7 | 3.5 | 2 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 8:01 | 0 | 267.75 | 1 | 8:09 | 460.5 | 260.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2630 | install rest of azdel | 100 | 50 | 2 | RS/BM |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 8:51 | 0 | 217.75 | 1 | 8:59 | 510.5 | 210.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2640 | Route Azdel Openings | 10 | 10 | 1 | [5 empty] | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 8:51 | 0 | 217.75 | 1 | 9:09 | 520.5 | 200.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2670 | Fasten Backers for Ducting and Above Cove | 15 | 15 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 8:51 | 0 | 217.75 | 1 | 9:24 | 535.5 | 185.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2680 | insulate entire exterior | 100 | 100 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 8:51 | 0 | 217.75 | 1 | 11:04 | 635.5 | 85.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2690 | Panel Interior Front Wall Bath |  |  | 0 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 8:51 | 0 | 217.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2700 | caulk exterior corners of wheelwells | 5 | 5 | 1 | RS |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 8:56 | 0 | 212.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2710 | cut all holes for switches & recepts | 30 | 30 | 1 | BM |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 9:26 | 0 | 182.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2720 | add backers for switches & recepts | 15 | 15 | 1 | BM |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 9:41 | 0 | 167.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2730 | install recepts | 45 | 45 | 1 | BM |  |  |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 10:26 | 0 | 122.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
2 | 2740 | install switches | 20 | 20 | 1 | BM | 1273.5 | 1.7669 |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 | 1 | 10:46 | 0 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
Station | Process_# |  |  | 0 | 0 |  | 8.5x24 | 206493 |  |  | 42690.3681 | 20 | 700.75 |  | 42690.3542 | 0 | 720.75 |  | 10:46 | 0 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1030 | Weld front radius wall x 2 | 20 | 20 | 1 | Heath |  |  |  | 1 | 42690.3819 | 40 | 680.75 |  | 42690.3542 | 0 | 720.75 |  | 10:46 | 0 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 0 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1040 | Roof Truss Setup Time | 15 | 15 | 1 | [5 empty] | 42690.3819 | 40 | 680.75 | 1 | 42690.3646 | 15 | 705.75 |  | 10:46 | 15 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 15 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1050 | Weld roof trusses (2 min ea) | 34 | 34 | 1 | [5 empty] | 42690.3819 | 40 | 680.75 | 1 | 42690.3882 | 49 | 671.75 |  | 10:46 | 49 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 49 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1060 | Weld roof parts together | 60 | 60 | 1 | [5 empty] | 42690.3819 | 40 | 680.75 | 1 | 42690.4299 | 109 | 611.75 |  | 10:46 | 109 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 109 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1070 | Table prep for 1 pc roof | 8 | 8 | 1 | Heath |  |  |  |  | 42690.3819 | 40 | 680.75 | 1 | 42690.4354 | 117 | 603.75 |  | 10:46 | 117 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 117 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1080 | Roof lay out | 17 | 8.5 | 2 | Heath |  |  |  | 1 | 42690.3875 | 48.5 | 672.25 | 1 | 42690.441 | 125.5 | 595.25 |  | 10:46 | 125.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 125.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1090 | Tack roof | 8 | 4 | 2 | Heath;Leon |  |  |  | 1 | 42690.3903 | 52.5 | 668.25 | 1 | 42690.4437 | 129.5 | 591.25 |  | 10:46 | 129.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 129.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1100 | Weld 1 pc roof | 24 | 12 | 2 | Heath;Leon |  |  |  | 1 | 42690.3986 | 64.5 | 656.25 | 1 | 42690.4521 | 141.5 | 579.25 |  | 10:46 | 141.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 141.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1110 | A/C Ducting - Single | 10 | 5 | 2 | Heath;Leon |  |  |  | 1 | 42690.4021 | 69.5 | 651.25 | 1 | 42690.4556 | 146.5 | 574.25 |  | 10:46 | 146.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 146.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1130 | Upper front wall | 30 | 30 | 1 |  |  |  | move up | 1 | 42690.4229 | 99.5 | 621.25 |  | 42690.4556 | 146.5 | 574.25 |  | 10:46 | 146.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 146.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1140 | Lower front wall | 15 | 15 | 1 |  |  |  | move up | 1 | 42690.4333 | 114.5 | 606.25 |  | 42690.4556 | 146.5 | 574.25 |  | 10:46 | 146.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 146.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1150 | Prep Table | 10 | 5 | 2 |  |  |  |  | 1 | 42690.4368 | 119.5 | 601.25 | 1 | 42690.459 | 151.5 | 569.25 |  | 10:46 | 151.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 151.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1160 | Rear wall header | 20 | 20 | 1 |  |  |  |  | 1 | 42690.4507 | 139.5 | 581.25 |  | 42690.459 | 151.5 | 569.25 |  | 10:46 | 151.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 151.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1170 | Lay Out C/S Sidewall | 70 | 35 | 2 | Heath;Leon |  |  |  | 1 | 42690.475 | 174.5 | 546.25 | 1 | 42690.4833 | 186.5 | 534.25 |  | 10:46 | 186.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 186.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1200 | Happijac - Rear | 5 | 2.5 | 2 |  |  |  |  | 1 | 42690.4764 | 177 | 543.75 | 1 | 42690.4847 | 189 | 531.75 |  | 10:46 | 189 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 189 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1230 | Sofa - CS - Rear | 3 | 1.5 | 2 |  |  |  |  | 1 | 42690.4771 | 178.5 | 542.25 | 1 | 42690.4854 | 190.5 | 530.25 |  | 10:46 | 190.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 190.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1240 | Dinette CS - Front | 3 | 1.5 | 2 |  |  |  |  | 1 | 42690.4778 | 180 | 540.75 | 1 | 42690.4861 | 192 | 528.75 |  | 10:46 | 192 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 192 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1280 | tack C/S sidewall | 52 | 26 | 2 | Heath;Leon |  |  |  | 1 | 42690.4958 | 206 | 514.75 | 1 | 42690.5042 | 218 | 502.75 |  | 10:46 | 218 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 218 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1290 | weld C/S sidewall | 42 | 21 | 2 | Heath;Leon |  |  |  | 1 | 42690.5104 | 227 | 493.75 | 1 | 42690.5187 | 239 | 481.75 |  | 10:46 | 239 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 239 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1310 | Grind; tape; flip; weld; grind C/S sidewall | 28 | 14 | 2 | Heath;Leon |  |  |  | 1 | 42690.5201 | 241 | 479.75 | 1 | 42690.5285 | 253 | 467.75 |  | 10:46 | 253 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 253 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1320 | Lay Out R/S Sidewall | 90 | 45 | 2 | Heath;Leon |  |  |  | 1 | 5:14 | 286 | 434.75 | 1 | 5:26 | 298 | 422.75 |  | 10:46 | 298 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 298 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1350 | Happijac - Rear | 5 | 2.5 | 2 |  |  |  |  | 1 | 5:16 | 288.5 | 432.25 | 1 | 5:28 | 300.5 | 420.25 |  | 10:46 | 300.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 300.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1370 | Sofa - RS - Rear | 3 | 1.5 | 2 |  |  |  |  | 1 | 5:17 | 290 | 430.75 | 1 | 5:29 | 302 | 418.75 |  | 10:46 | 302 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 302 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1410 | tack R/S sidewall | 20 | 10 | 2 | Heath;Leon |  |  |  | 1 | 5:27 | 300 | 420.75 | 1 | 5:39 | 312 | 408.75 |  | 10:46 | 312 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 312 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1420 | weld R/S sidewall | 60 | 30 | 2 | Heath;Leon |  |  |  | 1 | 5:57 | 330 | 390.75 | 1 | 6:09 | 342 | 378.75 |  | 10:46 | 342 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 342 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1440 | Grind; tape; flip; weld; grind R/S sidewall | 28 | 14 | 2 | Heath;Leon |  |  |  | 1 | 6:11 | 344 | 376.75 | 1 | 6:23 | 356 | 364.75 |  | 10:46 | 356 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 356 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1450 | prep table | 15 | 7.5 | 2 | Heath;Leon |  |  |  | 1 | 6:18 | 351.5 | 369.25 | 1 | 6:30 | 363.5 | 357.25 |  | 10:46 | 363.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 363.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1460 | Lay Out Frame | 105 | 52.5 | 2 | Heath;Leon |  |  |  | 1 | 7:10 | 404 | 316.75 | 1 | 7:22 | 416 | 304.75 |  | 10:46 | 416 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 416 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1470 | Airline Track | 5 | 2.5 | 2 |  |  |  |  | 1 | 7:12 | 406.5 | 314.25 | 1 | 7:24 | 418.5 | 302.25 |  | 10:46 | 418.5 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 418.5 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1480 | Tack Frame | 65 | 32.5 | 2 | Heath;Leon |  |  |  | 1 | 7:44 | 439 | 281.75 | 1 | 7:56 | 451 | 269.75 |  | 10:46 | 451 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 451 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1490 | Weld frame | 90 | 45 | 2 | Heath;Leon |  |  |  | 1 | 8:29 | 484 | 236.75 | 1 | 8:41 | 496 | 224.75 |  | 10:46 | 496 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 496 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1500 | 4in Addition Ht Sub Frame | 10 | 5 | 2 |  |  |  |  | 1 | 8:34 | 489 | 231.75 | 1 | 8:46 | 501 | 219.75 |  | 10:46 | 501 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 501 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1520 | Tongue Tray - Generator | 7 | 7 | 1 | [5 empty] | 8:34 | 489 | 231.75 | 1 | 8:53 | 508 | 212.75 |  | 10:46 | 508 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 508 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1530 | Drill Weep Holes | 10 | 10 | 1 |  |  |  |  | 1 | 8:44 | 499 | 221.75 |  | 8:53 | 508 | 212.75 |  | 10:46 | 508 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 508 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1540 | Fresh tank | 25 | 25 | 1 |  |  |  |  | 1 | 9:09 | 524 | 196.75 |  | 8:53 | 508 | 212.75 |  | 10:46 | 508 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 508 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1550 | Waste tanks | 15 | 15 | 1 |  |  |  |  | 1 | 9:24 | 539 | 181.75 |  | 8:53 | 508 | 212.75 |  | 10:46 | 508 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 508 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1560 | Fuel Tank | 25 | 25 | 1 | [5 empty] | 9:24 | 539 | 181.75 | 1 | 9:18 | 533 | 187.75 |  | 10:46 | 533 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 533 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1570 | Tank wiring and plumbing hook up | 70 | 70 | 1 |  |  |  |  | 1 | 10:34 | 609 | 111.75 |  | 9:18 | 533 | 187.75 |  | 10:46 | 533 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 533 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1580 | 3 Season Plumbing | 20 | 20 | 1 |  |  |  |  | 1 | 10:54 | 629 | 91.75 |  | 9:18 | 533 | 187.75 |  | 10:46 | 533 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 533 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1590 | Set Axles | 20 | 10 | 2 |  |  |  |  | 1 | 11:04 | 639 | 81.75 | 1 | 9:28 | 543 | 177.75 |  | 10:46 | 543 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 543 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1600 | Brake wires | 20 | 20 | 1 | [5 empty] | 11:04 | 639 | 81.75 | 1 | 9:48 | 563 | 157.75 |  | 10:46 | 563 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 563 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1610 | Stamp VIN on Frame | 3 | 3 | 1 |  |  |  |  | 1 | 11:07 | 642 | 78.75 |  | 9:48 | 563 | 157.75 |  | 10:46 | 563 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 563 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1620 | Run fuel lines & carb canister for Gen | 30 | 30 | 1 | [5 empty] | 11:07 | 642 | 78.75 | 1 | 10:18 | 593 | 127.75 |  | 10:46 | 593 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 593 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1630 | Run Fuel Line for Filling Station | 10 | 10 | 1 | [5 empty] | 11:07 | 642 | 78.75 | 1 | 10:28 | 603 | 117.75 |  | 10:46 | 603 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 603 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1640 | Install wheels | 15 | 15 | 1 | [5 empty] | 11:07 | 642 | 78.75 | 1 | 10:43 | 618 | 102.75 |  | 10:46 | 618 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 618 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1650 | Install Jacks; Sewer Hose; Spare Tire Rack; sewage hose holder | 25 | 25 | 1 |  |  |  |  | 1 | 11:32 | 667 | 53.75 |  | 10:43 | 618 | 102.75 |  | 10:46 | 618 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 618 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1660 | Fasten Water Line | 35 | 35 | 1 | [5 empty] | 11:32 | 667 | 53.75 | 1 | 11:18 | 653 | 67.75 |  | 10:46 | 653 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 653 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75
1 | 1670 | Fresh Water Fill and Vent Hoses | 5 | 5 | 1 |  | 1305 | 1.8106 |  |  | 11:32 | 667 | 53.75 | 1 | 11:23 | 658 | 62.75 |  | 10:46 | 658 | 102.75 |  | 11:04 | 635.5 | 85.25 |  | 10:22 | 658 | 128.75 |  | 10:20 | 590 | 130.75 |  |  | 9:43 | 553 | 167.75 |  | 10:31 | 601 | 119.75 |  | 10:34 | 604 | 116.75 |  | 8:21 | 471 | 249.75

## Sheet1
Primary, Secondary, Tertiary Personnel Assignment | Logic Makes Selections Based on Logic? Balanced Work Load ?

## St5 Input
Station | Process_# | Process_Name | 8.5x24 | People | Responsible | 206129
5 | 5060 | Ramp Door Install | 30 |  | NT
5 | 5080 | License Plate | 2 |  | NT
5 | 5090 | Grab Handles (Ramp) | 10 |  | NT
5 | 5100 | "Fire Ext. | 15 | 15 | 15
5 | 5110 | Clean Exterior | 35 |  | RW
5 | 5120 | Exterior Stickers and Logos | 20 |  | RW
5 | 5130 | Caulk Exterior | 45 |  | RW
5 | 5140 | Clean Interior | 80 |  | RW
5 | 5150 | Clean Interior - Cabinets CS Front | 5
5 | 5230 | Clean Interior - Happijac - Rear | 5
5 | 5260 | Clean Interior - Sofa - CS - Rear | 5
5 | 5280 | Clean Interior - Sofa - RS - Rear | 5
5 | 5340 | Insulation - floor | 10
5 | 5350 | Interior Stickers | 11 |  | RW
5 | 5360 | Caulk Interior | 70 |  | RW
5 | 5370 | Shower Curtain | 5 |  | RW
5 | 5380 | Grease Caps | 2 |  | RW
5 | 5390 | Tighten Wheel Lugs & check air presure in tires | 5 |  | RW
5 | 5400 | Install Graphics | 130 |  | RW
5 | 5440 | Tie Down Rings | 2 |  | RW
5 | 5450 | Hi-Pot Test | 10 |  | NT
5 | 5460 | Electrical Systems check | 45 |  | NT
5 | 5470 | Functionallity Test | 20 |  | NT
5 | 5510 | Functionallity Test - Happijac - Rear | 5
5 | 5540 | Functionallity Test - Sofa - CS - Rear | 5
5 | 5560 | Functionallity Test - Sofa - RS - Rear | 5
5 | 5650 | Functionallity Test - Stereo | 5
5 | 5710 | Inspection / Walk Through | 30
5 | 5720 | Standard Rework | 300
Station | Process_# | Process_Name | 7.0x20 | People | Responsible | 206173
4 | 4010 | Finish Water Heater | 10 |  | SR
4 | 4020 | Outside Water Fill | 6 |  | SR
4 | 4030 | Install Outside Shower | 5 |  | SR
4 | 4040 | LP Tray and Tanks | 7 |  | SR
4 | 4050 | install intellipower | 120 |  | TS
4 | 4060 | install battery disconnect & divider panal | 20 |  | TS
3 | 4080 | Interior Hook Up | 120 |  | TS
4 | 4110 | Install LP Lines | 30 |  | JR
4 | 4120 | Main Switch Panel Hook Up No Stereo 45 | 45 |  | TS
4 | 4150 | Fenders - 7 Wide | 15 |  | NT
4 | 4160 | Lower Rub Rail | 40 |  | NT
4 | 4180 | Wire Lower Clearance Lights | 15 |  | NT
4 | 4190 | Fender Lights - 7.0 Wide | 30 |  | NT
4 | 4200 | Flow Through Vents | 20 |  | NT
4 | 4220 | Install Motorbase | 15 |  | TS
4 | 4240 | Install Outside Coax | 15 |  | TS
4 | 4260 | Exterior Recept Install | 15 |  | TS
4 | 4280 | Exterior 12V Outlet | 10 |  | TS
4 | 4300 | Install Kitchen Overhead | 17 |  | JW
4 | 4310 | Set Refer | 30 |  | SR
4 | 4320 | Tail Lights - License Plate Light Installed | 60 |  | NT
4 | 4340 | Refer Hook Up | 14 |  | SR
4 | 4350 | Outside Refer Vent | 5 |  | SR
4 | 4360 | Outside Water Heater and Furnace Vent | 15 |  | JR
4 | 4380 | Install Outside Water Heater Door | 5 |  | JR
4 | 4390 | wire upper clearance lights | 35 |  | SR
4 | 4410 | Trim Ramp Door Opening | 20 |  | SR
4 | 4420 | Install Windows (All Std) | 30 |  | SR
4 | 4450 | Day and Night Shades | 20 |  | RW
4 | 4460 | ATP Kickplate | 45 |  | RW
4 | 4470 | Hook Up A/C (1st) | 31 |  | TS
4 | 4490 | Cove | 120 |  | RW
4 | 4500 | Trim Interior | 60 |  | RW
4 | 4520 | Vents Garnish - Roof | 5 |  | SR
4 | 4580 | Towel Bar | 8 |  | RW
4 | 4590 | Install Mirror | 5 |  | RW
4 | 4600 | Shower Curtain Rod | 5 |  | RW
4 | 4610 | Install Toilet | 7 |  | JR
4 | 4620 | LP Test - Water Test | 25 | 25 | SR
4 | 4650 | Install Entrance Door | 7 |  | NT
4 | 4670 | Grab Handle Entrance Door | 5 |  | NT
4 | 4680 | Trim Entrance Door | 20 |  | NT
4 | 4690 | Refer Panels | 5 |  | RW
4 | 4700 | Awning cradle | 5 |  | NT
4 | 4710 | Awning | 30 |  | NT
4 | 4720 | Front Baggage Door | 10 |  | NT
4 | 4730 | Bathdoor | 10 |  | RW
4 | 4740 | Trim Bathroom Door | 15 |  | RW
4 | 4780 | Prep Bed Door - RS | 33 |  | SR
4 | 4800 | Install Bed Door - RS | 217 |  | MH
4 | 4880 | Install Dinette CS - Rear | 45 |  | RW
4 | 4920 | Flood Test | 80 |  | SR
4 | 4970 | install & hook up LP tanks | 15 |  | SR
Station | Process_# | Process_Name | 7.0x20 | People | Responsible | 206112
3 | 3010 | install bathroom upper cab. & countertop | 37 |  | J.R.
3 | 3020 | install bath backsplash | 8 |  | J.R.
3 | 3030 | set linen in bathroom | 48 |  | J.R.
3 | 3040 | set kitchen broom closet | 50 |  | J.R.
3 | 3050 | install bargman cord & junction box | 65 |  | TS
3 | 3060 | wire electric jack | 10 |  | TS
3 | 3070 | Install Battery | 20 |  | TS
3 | 3100 | Loom Wires Where Needed | 27 |  | TS
3 | 3110 | Low point drains & water lines. (std. unit) | 26 |  | JR
3 | 3120 | Install Shower | 8 |  | JR
3 | 3130 | Shower Faucet | 2 |  | JR
3 | 3140 | Set Bath Wall and Drill Holes for Plumbing and Wiring | 20 |  | JR
3 | 3150 | Plumb Drain Vents | 10 |  | JR
3 | 3160 | Panel Interior Bathroom | 10 |  | JR
3 | 3170 | Panel Outside of Bath Wall | 9 |  | JR
3 | 3180 | Install remainder of ceiling panals | 30 |  | JR
3 | 3190 | Panel All Interior Walls | 120 |  | JR
3 | 3210 | Install and Hook Up Front Plumbing Kit | 13 |  | JR
3 | 3220 | Mount pump & hook up electric | 5 |  | JR
3 | 3230 | Install LP Lines | 20 |  | JR
3 | 3240 | Set Furnace and Install Furnace Vent | 20 |  | JR
3 | 3250 | Refer Cabinet | 9 |  | JR
3 | 3260 | Trim Refer Cabinet | 10 |  | JR
3 | 3270 | Finish installing shower (rivets) & shower head with accesseries | 18 |  | JR
3 | 3300 | Drill External Speaker Holes | 10 |  | MH
3 | 3310 | Install Water Heater | 10 |  | JR
3 | 3320 | Install Plumbing and Vent Pipes | 20 |  | JR
3 | 3330 | Insulate | 90 |  | RS
3 | 3340 | Insulate Front End | 5 |  | RS
3 | 3360 | Hang Rear Corners Stainless Steel | 8 |  | MH
3 | 3370 | Prep for CS Metal | 15 |  | MH
3 | 3380 | Degabond CS | 5 |  | MH
3 | 3390 | Hang CS Metal | 25 |  | MH
3 | 3420 | Route CS Metal | 10 |  | MH
3 | 3430 | Prep for RS Metal | 1 |  | MH
3 | 3440 | Degabond RS | 5 |  | MH
3 | 3450 | Hang RS Metal | 25 |  | MH
3 | 3480 | Route RS Metal | 10 |  | MH
3 | 3510 | Prep Front End Metal | 5 |  | MH
3 | 3520 | Metal Front End | 25 |  | MH
3 | 3530 | Gravel Guard | 20 |  | MH
3 | 3540 | Front Trim Pieces | 15 |  | MH
3 | 3550 | Route Baggage Doors | 5 |  | MH
3 | 3560 | Set Furnace and Install Furnace Vent | 17 |  | JR
3 | 3570 | Set Kitchen Base | 7 |  | JR
3 | 3580 | Insulate Roof | 28 |  | MH
3 | 3590 | Metal Roof and Degabond | 21 |  | MH
3 | 3600 | Bend Down Edge of Metal Roof | 10 |  | MH
3 | 3610 | Intall Front Roof Trim Piece | 10 |  | MH
3 | 3620 | Upper Rub Rail | 45 |  | MH
3 | 3630 | Awning Rail | 10 |  | MH
3 | 3640 | Upper Clearance Lights | 15 |  | MH
3 | 3660 | Holes for Plumbing Vents | 6 |  | MH
3 | 3670 | Route Roof Vents | 5 |  | MH
3 | 3690 | Install Vents and Seal MaxAir Brackets | 15 |  | MH
3 | 3710 | Install Plumbing and Vent Covers and Tail Pipes | 15 |  | MH
3 | 3750 | Clean Roof | 6 |  | MH
3 | 3760 | Seal Roof | 20 |  | MH
3 | 3770 | Seal Under Front Radius and Down Front Edge | 18 |  | MH
3 | 3780 | Refer Vent Cap | 2 |  | MH
3 | 3800 | Upper Flow Thru Vent - Scene Light - Speakers | 35 |  | MH
3 | 3810 | Seal Under Rub Rail | 20 |  | MH
3 | 3820 | Kitchen Plumbing | 20 |  | JR
3 | 3830 | Install Kitchen Counter Top | 9 |  | JR
3 | 3840 | install kitchen backsplash | 8 |  | JR
3 | 3850 | Wire Upper Cleanance and Loading Lights (Int. Hook Up) | 50 |  | MH
3 | 3880 | Flow Through Vents | 20 |  | MH
3 | 3900
Station | Process_# | Process_Name | 8.5x28FB | People | Responsible | 206511
2 | 2010 | Top weld and axles | 40 |  | Tator
2 | 2020 | Install Coupler | 15 |  | RS
2 | 2030 | Install D-Rings | 52 |  | RS
2 | 2050 | cut first piece of flooring (7' wide) |  |  | RS
2 | 2060 | Level Frame | 5 |  | BM
2 | 2070 | Grind Top Welds | 20 |  | RS
2 | 2080 | Set Wheel wells or Wheel Well Metal | 5 |  | RS
2 | 2090 | Install flooring ( 2 people) | 160 |  | BM
2 | 2120 | Drill Plumbing Holes and Toilet Drains | 12 |  | RS
2 | 2130 | Drill Holes for Gas Lines and Low Points | 10 |  | RS
2 | 2140 | install 3 inch grommmets for holes | 10 |  | BM
2 | 2150 | mark wall lines on floor/cover floor | 40 |  | RS
2 | 2160 | cover floor | 20 |  | BM
2 | 2170 | Set Walls - Rear Header - Front Walls | 30 |  | LS
2 | 2180 | Set and Weld Roof | 45 |  | LS
2 | 2190 | Final Weld on Sidewalls | 50 |  | LS
2 | 2200 | final weld on front walls | 20 |  | RS
2 | 2210 | Drill Holes for Wiring | 40 |  | RS
2 | 2220 | Grommet All Holes Where Needed | 10 |  | RS
2 | 2600 | Install Ground Wires | 10 |  | RS
2 | 2230 | Rough Wire Unit (Front Bedroom: 4.5 hrs) | 150 |  | BM
2 | 2300 | Dinette RS - Rear | 1
2 | 2320 | A/C - 1st | 8
2 | 2410 | Loading Lights | 3.5
2 | 2450 | Grind Sidewalls | 35 |  | RS
2 | 2460 | Square Front and Rear Ends | 10 |  | LS
2 | 2470 | Cut Out Flooring for Doorway | 10 |  | RS
2 | 2480 | Caulk Floor Around Outside Edge | 5 |  | RS
2 | 2490 | Radius Blocks in Window Corners | 10 |  | RS
2 | 2520 | Azdel Front End | 30 |  | RS
2 | 2530 | Set Interior Front Wall and Cage | 25 |  | RS
2 | 2540 | Water Shelf |  |  | RS
2 | 2550 | Water Heater Hookup |  |  | BM
2 | 2560 | Undercoat Wheel Well | 5 |  | RS
2 | 2570 | Paint at Openings (Windows - etc) | 5 |  | RS
2 | 2580 | VBH on End Tubes and at Wheels | 10 |  | RS
2 | 2590 | install /remove scaffold | 10
2 | 2610 | Azdel Inside Front Wall | 15 |  | RS
2 | 2620 | Install 1st Piece of Azdel On Each Side of Sidewall | 7 |  | RS
2 | 2630 | install rest of azdel | 100 |  | RS/BM
2 | 2640 | Route Azdel Openings | 10
2 | 2670 | Fasten Backers for Ducting and Above Cove | 15 |  | RS
2 | 2680 | insulate entire exterior | 100 |  | RS
2 | 2690 | Panel Interior Front Wall Bath |  |  | RS
2 | 2700 | caulk exterior corners of wheelwells | 5 |  | RS
2 | 2710 | cut all holes for switches & recepts | 30 |  | BM
2 | 2720 | add backers for switches & recepts | 15 |  | BM
2 | 2730 | install recepts | 45 |  | BM
2 | 2740 | install switches | 20 |  | BM
Station | Process_# | Process_Name | 8.5x24 | People | Responsible | 206493
1 | 1030 | Weld front radius wall x 2 | 20 | 1 | Heath
1 | 1040 | Roof Truss Setup Time | 15 | 1
1 | 1050 | Weld roof trusses (2 min ea) | 34 | 1
1 | 1060 | Weld roof parts together | 60 | 1
1 | 1070 | Table prep for 1 pc roof | 8 | 1 | Heath
1 | 1080 | Roof lay out | 17 | 1 | Heath
1 | 1090 | Tack roof | 8 | 2 | Heath;Leon
1 | 1100 | Weld 1 pc roof | 24 | 2 | Heath;Leon
1 | 1110 | A/C Ducting - Single | 10 | 2 | Heath;Leon
1 | 1130 | Upper front wall | 30 | 1
1 | 1140 | Lower front wall | 15 | 1
1 | 1150 | Prep Table | 10 | 1
1 | 1160 | Rear wall header | 20 | 1
1 | 1170 | Lay Out C/S Sidewall | 70 | 2 | Heath;Leon
1 | 1200 | Happijac - Rear | 5 | 1
1 | 1230 | Sofa - CS - Rear | 3 | 1
1 | 1240 | Dinette CS - Front | 3 | 1
1 | 1280 | tack C/S sidewall | 52 | 2 | Heath;Leon
1 | 1290 | weld C/S sidewall | 42 | 2 | Heath;Leon
1 | 1310 | Grind; tape; flip; weld; grind C/S sidewall | 28 | 2 | Heath;Leon
1 | 1320 | Lay Out R/S Sidewall | 90 | 2 | Heath;Leon
1 | 1350 | Happijac - Rear | 5 | 1
1 | 1370 | Sofa - RS - Rear | 3 | 1
1 | 1410 | tack R/S sidewall | 20 | 2 | Heath;Leon
1 | 1420 | weld R/S sidewall | 60 | 2 | Heath;Leon
1 | 1440 | Grind; tape; flip; weld; grind R/S sidewall | 28 | 2 | Heath;Leon
1 | 1450 | prep table | 15 | 2 | Heath;Leon
1 | 1460 | Lay Out Frame | 105 | 2 | Heath;Leon
1 | 1470 | Airline Track | 5 | 1
1 | 1480 | Tack Frame | 65 | 2 | Heath;Leon
1 | 1490 | Weld frame | 90 | 2 | Heath;Leon
1 | 1500 | 4in Addition Ht Sub Frame | 10 | 1
1 | 1520 | Tongue Tray - Generator | 7 | 1
1 | 1530 | Drill Weep Holes | 10 | 1
1 | 1540 | Fresh tank | 25 | 1
1 | 1550 | Waste tanks | 15 | 1
1 | 1560 | Fuel Tank | 25 | 1
1 | 1570 | Tank wiring and plumbing hook up | 70 | 1
1 | 1580 | 3 Season Plumbing | 20 | 1
1 | 1590 | Set Axles | 20 | 1
1 | 1600 | Brake wires | 20 | 1
1 | 1610 | Stamp VIN on Frame | 3 | 1
1 | 1620 | Run fuel lines & carb canister for Gen | 30 | 1
1 | 1630 | Run Fuel Line for Filling Station | 10 | 1
1 | 1640 | Install wheels | 15 | 1
1 | 1650 | Install Jacks; Sewer Hose; Spare Tire Rack; sewage hose holder | 25 | 1
1 | 1660 | Fasten Water Line | 35 | 1
1 | 1670 | Fresh Water Fill and Vent Hoses | 5 | 1