## St4
|  | Shift Start | 5:05 | [7 empty] | Cristy Miller
|  | Break Start Time | 8:50 | [7 empty] | Tony Chupp
|  | Break End Time | 9:05 | [7 empty] | Gary Schabach
|  | Shift End | 13:05 | [7 empty] | Leon Schwartz
|  | Start Time | 2016-11-11 07:45 | [7 empty] | Braydon Martin
End Time
|  | Number of People | 8
|  | TAKT | 1.65 | DAYS
|  | Minutes Per Person Per Takt | 742.5 | min
|  | Minutes per TAKT (7.5 hr day) | 5940 | min
|  | Minutes per TAKT (Working Time) | 6138 | 767.25
|  | Predicted Schedule Time | 6265.5 | 783.1875
|  | Available Time | -127.5
Actual Scheduled Time
Station | Process_# | Process_Name | 7.0x20 | People | Comments / Issues |  | Heath Hawkins |  |  |  | Leon Hochstetler |  |  |  | Merle Farmwald |  |  |  | Mike Hochstetler |  |  |  | JR Wood |  |  |  | Rob Smith |  |  |  | Brian Miller |  |  |  | Steve Rodman |  |  |  | Nate Turner |  |  |  | Rex Wert
5 | 5060 | Ramp Door Install | 30 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.3438 | 30 | 6108
5 | 5080 | License Plate | 2 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.3451 | 32 | 6106
5 | 5090 | Grab Handles (Ramp) | 10 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.3521 | 42 | 6096
5 | 5100 | Fire Ext. - LP Detector - Carbon Monoxide Detector | 15 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.3625 | 57 | 6081
5 | 5110 | Clean Exterior | 35 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.3868 | 92 | 6046
5 | 5120 | Exterior Stickers and Logos | 20 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.4007 | 112 | 6026
5 | 5130 | Caulk Exterior | 40 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.4285 | 152 | 5986
5 | 5140 | Clean Interior | 70 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.4771 | 222 | 5916
5 | 5210 | Clean - Bed Door - RS | 5 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.4806 | 227 | 5911
5 | 5310 | Dinette CS - Rear | 5 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.484 | 232 | 5906
5 | 5350 | Interior Stickers | 11 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.4917 | 243 | 5895
5 | 5360 | Caulk Interior | 60 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.5333 | 303 | 5835
5 | 5370 | Shower Curtain | 5 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.5368 | 308 | 5830
5 | 5380 | Grease Caps | 2 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.5382 | 310 | 5828
5 | 5390 | Tighten Wheel Lugs & check air presure in tires | 5 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 42685.5417 | 315 | 5823
5 | 5400 | Install Graphics | 120 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 7:00 | 435 | 5703
5 | 5440 | Tie Down Rings | 2 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 | 1 | 7:02 | 437 | 5701
5 | 5450 | Hi-Pot Test | 10 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
5 | 5460 | Electrical Systems check | 45 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
5 | 5470 | functionallity test | 20 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
5 | 5490 | Bed Door - RS | 5 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
5 | 5590 | Dinette CS - Rear | 5 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
5 | 5710 | Inspection / Walk Through | 30 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
5 | 5720 | Standard Rework | 300 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
|  |  |  | 852 | 1.1105 |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4010 | Finish Water Heater | 10 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4020 | Outside Water Fill | 6 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4040 | LP Tray and Tanks | 7 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4050 | install intellipower | 120 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4060 | install battery disconnect & divider panal | 20 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
3 | 4080 | Interior Hook Up | 120 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4100 | Trim Exterior Metal for Wheel Wells (8.5' wide only) | [5 empty] | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4110 | Install LP Lines | 30 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4120 | Main Switch Panel Hook Up No Stereo 45 | 45 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4130 | 3 Season Plumbing | 5 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4140 | Radio Hook up | 8 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4150 | Fenders - 7 Wide | 15 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4160 | Lower Rub Rail | 40 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4180 | Wire Lower Clearance Lights | 15 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4190 | Fender Lights - 7.0 Wide | 30 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4200 | Flow Through Vents | 20 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4220 | Install Motorbase | 15 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4240 | Install Outside Coax | 15 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4260 | Exterior Recept Install | 15 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4280 | Exterior 12V Outlet | 10 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4300 | Install Kitchen Overhead | 17 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4310 | Set Refer | 30 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4320 | "Tail Lights | 60 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4340 | Refer Hook Up | 14 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4350 | Outside Refer Vent | 5 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4360 | Outside Water Heater and Furnace Vent | 15 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4380 | Install Outside Water Heater Door | 5 |  |  |  |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 42685.3229 | 0 | 6138 |  | 7:02 | 437 | 5701
4 | 4390 | wire upper clearance lights | 35
4 | 4410 | Trim Ramp Door Opening | 20
4 | 4420 | Install Windows (All Std) | 30
4 | 4450 | Day and Night Shades | 20
4 | 4460 | ATP Kickplate | 45
4 | 4490 | Cove | 120
4 | 4500 | Trim Interior | 60
4 | 4510 | Speaker Covers | 10
4 | 4520 | Vents Garnish - Roof | 5
4 | 4550 | Install - Cabinets CS Rear | 30
4 | 4580 | Towel Bar | 8
4 | 4590 | Install Mirror | 5
4 | 4600 | Shower Curtain Rod | 5
4 | 4610 | Install Toilet | 7
4 | 4620 | "LP Test | 25
4 | 4650 | Install Entrance Door | 7
4 | 4670 | Grab Handle Entrance Door | 5
4 | 4680 | Trim Entrance Door | 20
4 | 4690 | Refer Panels | 5
4 | 4700 | Awning cradle | 5
4 | 4710 | Awning | 30
4 | 4720 | Front Baggage Door | 10
4 | 4730 | Bathdoor | 10
4 | 4740 | Trim Bathroom Door | 15
4 | 4780 | Prep Bed Door - RS | 33
4 | 4800 | Install Bed Door - RS | 217
4 | 4910 | Install Vinyl Zippered Rear Opening | 20
4 | 4920 | Flood Test | 80
4 | 4970 | install & hook up LP tanks | 15
|  |  |  | 1589 | 2.071
3 | 3010 | install bathroom upper cab. & countertop | 37
3 | 3020 | install bath backsplash | 8
3 | 3030 | set linen in bathroom | 48
3 | 3040 | set kitchen broom closet | 50
3 | 3050 | install bargman cord & junction box | 65
3 | 3060 | wire electric jack | 10
3 | 3070 | Install Battery | 20
3 | 3100 | Loom Wires Where Needed | 27
3 | 3110 | Low point drains & water lines. (std. unit) | 26
3 | 3120 | Install Shower | 8
3 | 3130 | Shower Faucet | 2
3 | 3140 | Set Bath Wall and Drill Holes for Plumbing and Wiring | 20
3 | 3150 | Plumb Drain Vents | 10
3 | 3160 | Panel Interior Bathroom | 10
3 | 3170 | Panel Outside of Bath Wall | 9
3 | 3180 | Install remainder of ceiling panals | 30
3 | 3190 | Panel All Interior Walls | 120
3 | 3210 | Install and Hook Up Front Plumbing Kit | 13
3 | 3220 | Mount pump & hook up electric | 5
3 | 3230 | Install LP Lines | 20
3 | 3240 | Set Furnace and Install Furnace Vent | 20
3 | 3250 | Refer Cabinet | 9
3 | 3260 | Trim Refer Cabinet | 10
3 | 3270 | Finish installing shower (rivets) & shower head with accesseries | 18
3 | 3300 | Drill External Speaker Holes | 10
3 | 3310 | Install Water Heater | 10
3 | 3320 | Install Plumbing and Vent Pipes | 20
3 | 3330 | Insulate | 100
3 | 3340 | Insulate Front End | 5
3 | 3360 | Hang Rear Corners Stainless Steel | 8
3 | 3370 | Prep for CS Metal | 15
3 | 3380 | Degabond CS | 5
3 | 3390 | Hang CS Metal | 30
3 | 3420 | Route CS Metal | 10
3 | 3430 | Prep for RS Metal | 1
3 | 3440 | Degabond RS | 5
3 | 3450 | Hang RS Metal | 25
3 | 3480 | Route RS Metal | 10
3 | 3490 | route exterior shower | 1
3 | 3500 | install flood lights | 8
3 | 3510 | Prep Front End Metal | 5
3 | 3520 | Metal Front End | 25
3 | 3530 | Gravel Guard | 20
3 | 3540 | Front Trim Pieces | 15
3 | 3550 | Route Baggage Doors | 5
3 | 3560 | Set Furnace and Install Furnace Vent | 17
3 | 3570 | Set Kitchen Base | 7
3 | 3580 | Insulate Roof | 28
3 | 3590 | Metal Roof and Degabond | 21
3 | 3600 | Bend Down Edge of Metal Roof | 12
3 | 3610 | Intall Front Roof Trim Piece | 10
3 | 3620 | Upper Rub Rail | 48
3 | 3630 | Awning Rail | 10
3 | 3640 | Upper Clearance Lights | 15
3 | 3660 | Holes for Plumbing Vents | 6
3 | 3670 | Route Roof Vents | 5
3 | 3680 | Set AC | 5
3 | 3690 | Install Vents and Seal MaxAir Brackets | 15
3 | 3710 | Install Plumbing and Vent Covers and Tail Pipes | 15
3 | 3750 | Clean Roof | 6
3 | 3760 | Seal Roof | 20
3 | 3770 | Seal Under Front Radius and Down Front Edge | 18
3 | 3780 | Refer Vent Cap | 2
3 | 3790 | digital antenna | 10
3 | 3800 | Upper Flow Thru Vent - Scene Light - Speakers | 35
3 | 3810 | Seal Under Rub Rail | 20
3 | 3820 | Kitchen Plumbing | 20
3 | 3830 | Install Kitchen Counter Top | 9
3 | 3840 | install kitchen backsplash | 8
3 | 3850 | Wire Upper Cleanance and Loading Lights (Int. Hook Up) | 50
3 | 3860 | drill holes for scene lights | 2
3 | 3870 | install scene lights | 10
3 | 3880 | Flow Through Vents | 20
3 | 3890 | Trim Wheel Wells (8.5' wide only) | 10
|  |  |  | 1382 | 1.8012
2 | 2010 | Top weld and axles | 40
2 | 2020 | Install Coupler | 15
2 | 2040 | Cut A-Track Slots | 25
2 | 2050 | cut first piece of flooring (7' wide) | 0
2 | 2060 | Level Frame | 5
2 | 2070 | Grind Top Welds | 15
2 | 2080 | Set Wheel wells or Wheel Well Metal | 5
2 | 2090 | Install flooring ( 2 people) | 160
2 | 2100 | Weld in A-Track Backer | 35
2 | 2110 | Install A-Track | 58
2 | 2120 | Drill Plumbing Holes and Toilet Drains | 12
2 | 2130 | Drill Holes for Gas Lines and Low Points | 10
2 | 2140 | install 3'' grommmets for holes | 10
2 | 2150 | mark wall lines on floor/cover floor | 25
2 | 2160 | cover floor | 20
2 | 2170 | Set Walls - Rear Header - Front Walls | 30
2 | 2180 | Set and Weld Roof | 40
2 | 2190 | Final Weld on Sidewalls | 45
2 | 2200 | final weld on front walls | 20
2 | 2210 | Drill Holes for Wiring | 30
2 | 2220 | Grommet All Holes Where Needed | 10
2 | 2600 | Install Ground Wires | 10
2 | 2230 | Rough Wire Unit (Front Bedroom: 4.5 hrs) | 125
2 | 2250 | Happijac - Rear | 7.5
2 | 2260 | Dinette CS - Front | 1
2 | 2320 | A/C - 1st | 8
2 | 2390 | Stereo | 9
2 | 2450 | Grind Sidewalls | 25
2 | 2460 | Square Front and Rear Ends | 10
2 | 2470 | Cut Out Flooring for Doorway | 10
2 | 2480 | Caulk Floor Around Outside Edge | 5
2 | 2490 | Radius Blocks in Window Corners | 10
2 | 2520 | Azdel Front End | 30
2 | 2530 | Set Interior Front Wall and Cage | 35
2 | 2540 | Water Shelf | 10
2 | 2550 | Water Heater Hookup | 15
2 | 2560 | Undercoat Wheel Well | 5
2 | 2570 | Paint at Openings (Windows - etc) | 5
2 | 2580 | VBH on End Tubes and at Wheels | 10
2 | 2590 | install /remove scaffold | 10
2 | 2610 | Azdel Inside Front Wall | 15
2 | 2620 | Install 1st Piece of Azdel On Each Side of Sidewall | 7
2 | 2630 | install rest of azdel | 80
2 | 2640 | Route Azdel Openings | 10
2 | 2670 | Fasten Backers for Ducting and Above Cove | 15
2 | 2680 | insulate entire exterior | 85
2 | 2690 | Panel Interior Front Wall Bath | 10
2 | 2700 | caulk exterior corners of wheelwells | 5
2 | 2710 | cut all holes for switches & recepts | 30
2 | 2720 | add backers for switches & recepts | 15
2 | 2730 | install recepts | 35
2 | 2740 | install switches | 20
|  |  |  | 1277.5 | 1.665
1 | 1030 | Weld front radius wall x 2 | 20 | 1
1 | 1040 | Roof Truss Setup Time | 15 | 1
1 | 1050 | Weld roof trusses (2 min ea) | 30 | 1
1 | 1060 | Weld roof parts together | 60 | 1
1 | 1070 | Table prep for 1 pc roof | 8 | 1
1 | 1080 | Roof lay out | 15 | 1
1 | 1090 | Tack roof | 8 | 2
1 | 1100 | Weld 1 pc roof | 20 | 2
1 | 1110 | A/C Ducting - Single | 10 | 2
1 | 1130 | Upper front wall | 30 | 1
1 | 1140 | Lower front wall | 15 | 1
1 | 1150 | Prep Table | 10 | 1
1 | 1160 | Rear wall header | 20 | 1
1 | 1170 | Lay Out C/S Sidewall | 65 | 2
1 | 1240 | Dinette CS - Front | 3 | 1
1 | 1280 | tack C/S sidewall | 50 | 2
1 | 1290 | weld C/S sidewall | 60 | 2
1 | 1310 | Grind; tape; flip; weld; grind C/S sidewall | 24 | 2
1 | 1320 | Lay Out R/S Sidewall | 90 | 2
1 | 1370 | Sofa - RS - Rear | 3 | 1
1 | 1410 | tack R/S sidewall | 20 | 2
1 | 1420 | weld R/S sidewall | 60 | 2
1 | 1440 | Grind; tape; flip; weld; grind R/S sidewall | 24 | 2
1 | 1450 | prep table | 15 | 2
1 | 1460 | Lay Out Frame | 65 | 2
1 | 1470 | Airline Track | 5 | 1
1 | 1480 | Tack Frame | 60 | 2
1 | 1490 | Weld frame | 80 | 2
1 | 1500 | 4in Addition Ht Sub Frame | 10 | 1
1 | 1510 | Tongue Tray - STD | 7 | 1
1 | 1530 | Drill Weep Holes | 10 | 1
1 | 1540 | Fresh tank | 25 | 1
1 | 1550 | Waste tanks | 15 | 1
1 | 1570 | Tank wiring and plumbing hook up | 70 | 1
1 | 1580 | 3 Season Plumbing | 20 | 1
1 | 1590 | Set Axles | 20 | 1
1 | 1600 | Brake wires | 20 | 1
1 | 1610 | Stamp VIN on Frame | 3 | 1
1 | 1640 | Install wheels | 15 | 1
1 | 1650 | Install Jacks; Sewer Hose; Spare Tire Rack; sewage hose holder | 25 | 1
1 | 1660 | Fasten Water Line | 35 | 1
1 | 1670 | Fresh Water Fill and Vent Hoses | 5 | 1
|  |  |  | 1165 | 1.5184
[5 empty] | 6265.5 | min
[5 empty] | 104.425 | hrs
[5 empty] | 11.6028 | 11 man-hrs

## St5 Input
Station | Process_# | Process_Name | 7.0x20 | People | Responsible
5 | 5060 | Ramp Door Install | 30 |  | NT
5 | 5080 | License Plate | 2 |  | NT
5 | 5090 | Grab Handles (Ramp) | 10 |  | NT
5 | 5100 | Fire Ext. - LP Detector - Carbon Monoxide Detector | 15 |  | RW
5 | 5110 | Clean Exterior | 35 |  | RW
5 | 5120 | Exterior Stickers and Logos | 20 |  | RW
5 | 5130 | Caulk Exterior | 40 |  | RW
5 | 5140 | Clean Interior | 70 |  | RW
5 | 5210 | Clean - Bed Door - RS | 5
5 | 5310 | Dinette CS - Rear | 5
5 | 5350 | Interior Stickers | 11 |  | RW
5 | 5360 | Caulk Interior | 60 |  | RW
5 | 5370 | Shower Curtain | 5 |  | RW
5 | 5380 | Grease Caps | 2 |  | RW
5 | 5390 | Tighten Wheel Lugs & check air presure in tires | 5 |  | RW
5 | 5400 | Install Graphics | 120 |  | RW
5 | 5440 | Tie Down Rings | 2 |  | RW
5 | 5450 | Hi-Pot Test | 10 |  | NT
5 | 5460 | Electrical Systems check | 45 |  | NT
5 | 5470 | functionallity test | 20 |  | NT
5 | 5490 | Bed Door - RS | 5
5 | 5590 | Dinette CS - Rear | 5
5 | 5710 | Inspection / Walk Through | 30
5 | 5720 | Standard Rework | 300
Station | Process_# | Process_Name | 7.0x20 | People | Responsible
4 | 4010 | Finish Water Heater | 10 |  | SR
4 | 4020 | Outside Water Fill | 6 |  | SR
4 | 4040 | LP Tray and Tanks | 7 |  | SR
4 | 4050 | install intellipower | 120 |  | TS
4 | 4060 | install battery disconnect & divider panal | 20 |  | TS
3 | 4080 | Interior Hook Up | 120 |  | TS
4 | 4100 | Trim Exterior Metal for Wheel Wells (8.5' wide only) |  |  | NT
4 | 4110 | Install LP Lines | 30 |  | JR
4 | 4120 | Main Switch Panel Hook Up No Stereo 45 | 45 |  | TS
4 | 4130 | 3 Season Plumbing | 5 |  | TS
4 | 4140 | Radio Hook up | 8 |  | TS
4 | 4150 | Fenders - 7 Wide | 15 |  | NT
4 | 4160 | Lower Rub Rail | 40 |  | NT
4 | 4180 | Wire Lower Clearance Lights | 15 |  | NT
4 | 4190 | Fender Lights - 7.0 Wide | 30 |  | NT
4 | 4200 | Flow Through Vents | 20 |  | NT
4 | 4220 | Install Motorbase | 15 |  | TS
4 | 4240 | Install Outside Coax | 15 |  | TS
4 | 4260 | Exterior Recept Install | 15 |  | TS
4 | 4280 | Exterior 12V Outlet | 10 |  | TS
4 | 4300 | Install Kitchen Overhead | 17 |  | JW
4 | 4310 | Set Refer | 30 |  | SR
4 | 4320 | "Tail Lights |  | 60
4 | 4340 | Refer Hook Up | 14 |  | SR
4 | 4350 | Outside Refer Vent | 5 |  | SR
4 | 4360 | Outside Water Heater and Furnace Vent | 15 |  | JR
4 | 4380 | Install Outside Water Heater Door | 5 |  | JR
4 | 4390 | wire upper clearance lights | 35 |  | SR
4 | 4410 | Trim Ramp Door Opening | 20 |  | SR
4 | 4420 | Install Windows (All Std) | 30 |  | SR
4 | 4450 | Day and Night Shades | 20 |  | RW
4 | 4460 | ATP Kickplate | 45 |  | RW
4 | 4490 | Cove | 120 |  | RW
4 | 4500 | Trim Interior | 60 |  | RW
4 | 4510 | Speaker Covers | 10 |  | RW
4 | 4520 | Vents Garnish - Roof | 5 |  | SR
4 | 4550 | Install - Cabinets CS Rear | 30 |  | JW
4 | 4580 | Towel Bar | 8 |  | RW
4 | 4590 | Install Mirror | 5 |  | RW
4 | 4600 | Shower Curtain Rod | 5 |  | RW
4 | 4610 | Install Toilet | 7 |  | JR
4 | 4620 | "LP Test |  | 25 | 25
4 | 4650 | Install Entrance Door | 7 |  | NT
4 | 4670 | Grab Handle Entrance Door | 5 |  | NT
4 | 4680 | Trim Entrance Door | 20 |  | NT
4 | 4690 | Refer Panels | 5 |  | RW
4 | 4700 | Awning cradle | 5 |  | NT
4 | 4710 | Awning | 30 |  | NT
4 | 4720 | Front Baggage Door | 10 |  | NT
4 | 4730 | Bathdoor | 10 |  | RW
4 | 4740 | Trim Bathroom Door | 15 |  | RW
4 | 4780 | Prep Bed Door - RS | 33 |  | SR
4 | 4800 | Install Bed Door - RS | 217 |  | MH
4 | 4910 | Install Vinyl Zippered Rear Opening | 20 |  | RW
4 | 4920 | Flood Test | 80 |  | SR
4 | 4970 | install & hook up LP tanks | 15 |  | SR
Station | Process_# | Process_Name | 8.5x24 | People | Responsible
3 | 3010 | install bathroom upper cab. & countertop | 37 |  | J.R.
3 | 3020 | install bath backsplash | 8 |  | J.R.
3 | 3030 | set linen in bathroom | 48 |  | J.R.
3 | 3040 | set kitchen broom closet | 50 |  | J.R.
3 | 3050 | install bargman cord & junction box | 65 |  | TS
3 | 3060 | wire electric jack | 10 |  | TS
3 | 3070 | Install Battery | 20 |  | TS
3 | 3100 | Loom Wires Where Needed | 27 |  | TS
3 | 3110 | Low point drains & water lines. (std. unit) | 26 |  | JR
3 | 3120 | Install Shower | 8 |  | JR
3 | 3130 | Shower Faucet | 2 |  | JR
3 | 3140 | Set Bath Wall and Drill Holes for Plumbing and Wiring | 20 |  | JR
3 | 3150 | Plumb Drain Vents | 10 |  | JR
3 | 3160 | Panel Interior Bathroom | 10 |  | JR
3 | 3170 | Panel Outside of Bath Wall | 9 |  | JR
3 | 3180 | Install remainder of ceiling panals | 30 |  | JR
3 | 3190 | Panel All Interior Walls | 120 |  | JR
3 | 3210 | Install and Hook Up Front Plumbing Kit | 13 |  | JR
3 | 3220 | Mount pump & hook up electric | 5 |  | JR
3 | 3230 | Install LP Lines | 20 |  | JR
3 | 3240 | Set Furnace and Install Furnace Vent | 20 |  | JR
3 | 3250 | Refer Cabinet | 9 |  | JR
3 | 3260 | Trim Refer Cabinet | 10 |  | JR
3 | 3270 | Finish installing shower (rivets) & shower head with accesseries | 18 |  | JR
3 | 3300 | Drill External Speaker Holes | 10 |  | MH
3 | 3310 | Install Water Heater | 10 |  | JR
3 | 3320 | Install Plumbing and Vent Pipes | 20 |  | JR
3 | 3330 | Insulate | 100 |  | RS
3 | 3340 | Insulate Front End | 5 |  | RS
3 | 3360 | Hang Rear Corners Stainless Steel | 8 |  | MH
3 | 3370 | Prep for CS Metal | 15 |  | MH
3 | 3380 | Degabond CS | 5 |  | MH
3 | 3390 | Hang CS Metal | 30 |  | MH
3 | 3420 | Route CS Metal | 10 |  | MH
3 | 3430 | Prep for RS Metal | 1 |  | MH
3 | 3440 | Degabond RS | 5 |  | MH
3 | 3450 | Hang RS Metal | 25 |  | MH
3 | 3480 | Route RS Metal | 10 |  | MH
3 | 3490 | route exterior shower | 1 |  | MH
3 | 3500 | install flood lights | 8 |  | MH
3 | 3510 | Prep Front End Metal | 5 |  | MH
3 | 3520 | Metal Front End | 25 |  | MH
3 | 3530 | Gravel Guard | 20 |  | MH
3 | 3540 | Front Trim Pieces | 15 |  | MH
3 | 3550 | Route Baggage Doors | 5 |  | MH
3 | 3560 | Set Furnace and Install Furnace Vent | 17 |  | JR
3 | 3570 | Set Kitchen Base | 7 |  | JR
3 | 3580 | Insulate Roof | 28 |  | MH
3 | 3590 | Metal Roof and Degabond | 21 |  | MH
3 | 3600 | Bend Down Edge of Metal Roof | 12 |  | MH
3 | 3610 | Intall Front Roof Trim Piece | 10 |  | MH
3 | 3620 | Upper Rub Rail | 48 |  | MH
3 | 3630 | Awning Rail | 10 |  | MH
3 | 3640 | Upper Clearance Lights | 15 |  | MH
3 | 3660 | Holes for Plumbing Vents | 6 |  | MH
3 | 3670 | Route Roof Vents | 5 |  | MH
3 | 3680 | Set AC | 5 |  | MH
3 | 3690 | Install Vents and Seal MaxAir Brackets | 15 |  | MH
3 | 3710 | Install Plumbing and Vent Covers and Tail Pipes | 15 |  | MH
3 | 3750 | Clean Roof | 6 |  | MH
3 | 3760 | Seal Roof | 20 |  | MH
3 | 3770 | Seal Under Front Radius and Down Front Edge | 18 |  | MH
3 | 3780 | Refer Vent Cap | 2 |  | MH
3 | 3790 | digital antenna | 10 |  | MH
3 | 3800 | Upper Flow Thru Vent - Scene Light - Speakers | 35 |  | MH
3 | 3810 | Seal Under Rub Rail | 20 |  | MH
3 | 3820 | Kitchen Plumbing | 20 |  | JR
3 | 3830 | Install Kitchen Counter Top | 9 |  | JR
3 | 3840 | install kitchen backsplash | 8 |  | JR
3 | 3850 | Wire Upper Cleanance and Loading Lights (Int. Hook Up) | 50 |  | MH
3 | 3860 | drill holes for scene lights | 2 |  | MH
3 | 3870 | install scene lights | 10 |  | MH
3 | 3880 | Flow Through Vents | 20 |  | MH
3 | 3890 | Trim Wheel Wells (8.5' wide only) | 10 |  | MH
Station | Process_# | Process_Name | 8.5x20 | People | Responsible
2 | 2010 | Top weld and axles | 40 |  | Tator
2 | 2020 | Install Coupler | 15 |  | RS
2 | 2040 | Cut A-Track Slots | 25 |  | RS
2 | 2050 | cut first piece of flooring (7' wide) | 0 |  | RS
2 | 2060 | Level Frame | 5 |  | BM
2 | 2070 | Grind Top Welds | 15 |  | RS
2 | 2080 | Set Wheel wells or Wheel Well Metal | 5 |  | RS
2 | 2090 | Install flooring ( 2 people) | 160 |  | BM
2 | 2100 | Weld in A-Track Backer | 35 |  | LS
2 | 2110 | Install A-Track | 58 |  | RS
2 | 2120 | Drill Plumbing Holes and Toilet Drains | 12 |  | RS
2 | 2130 | Drill Holes for Gas Lines and Low Points | 10 |  | RS
2 | 2140 | install 3'' grommmets for holes | 10 |  | BM
2 | 2150 | mark wall lines on floor/cover floor | 25 |  | RS
2 | 2160 | cover floor | 20 |  | BM
2 | 2170 | Set Walls - Rear Header - Front Walls | 30 |  | LS
2 | 2180 | Set and Weld Roof | 40 |  | LS
2 | 2190 | Final Weld on Sidewalls | 45 |  | LS
2 | 2200 | final weld on front walls | 20 |  | RS
2 | 2210 | Drill Holes for Wiring | 30 |  | RS
2 | 2220 | Grommet All Holes Where Needed | 10 |  | RS
2 | 2600 | Install Ground Wires | 10 |  | RS
2 | 2230 | Rough Wire Unit (Front Bedroom: 4.5 hrs) | 125 |  | BM
2 | 2250 | Happijac - Rear | 7.5
2 | 2260 | Dinette CS - Front | 1
2 | 2320 | A/C - 1st | 8
2 | 2390 | Stereo | 9
2 | 2450 | Grind Sidewalls | 25 |  | RS
2 | 2460 | Square Front and Rear Ends | 10 |  | LS
2 | 2470 | Cut Out Flooring for Doorway | 10 |  | RS
2 | 2480 | Caulk Floor Around Outside Edge | 5 |  | RS
2 | 2490 | Radius Blocks in Window Corners | 10 |  | RS
2 | 2520 | Azdel Front End | 30 |  | RS
2 | 2530 | Set Interior Front Wall and Cage | 35 |  | RS
2 | 2540 | Water Shelf | 10 |  | RS
2 | 2550 | Water Heater Hookup | 15 |  | BM
2 | 2560 | Undercoat Wheel Well | 5 |  | RS
2 | 2570 | Paint at Openings (Windows - etc) | 5 |  | RS
2 | 2580 | VBH on End Tubes and at Wheels | 10 |  | RS
2 | 2590 | install /remove scaffold | 10
2 | 2610 | Azdel Inside Front Wall | 15 |  | RS
2 | 2620 | Install 1st Piece of Azdel On Each Side of Sidewall | 7 |  | RS
2 | 2630 | install rest of azdel | 80 |  | RS/BM
2 | 2640 | Route Azdel Openings | 10
2 | 2670 | Fasten Backers for Ducting and Above Cove | 15 |  | RS
2 | 2680 | insulate entire exterior | 85 |  | RS
2 | 2690 | Panel Interior Front Wall Bath | 10 |  | RS
2 | 2700 | caulk exterior corners of wheelwells | 5 |  | RS
2 | 2710 | cut all holes for switches & recepts | 30 |  | BM
2 | 2720 | add backers for switches & recepts | 15 |  | BM
2 | 2730 | install recepts | 35 |  | BM
2 | 2740 | install switches | 20 |  | BM
Station | Process_# | Process_Name | 8.5x20 | People | Responsible
1 | 1030 | Weld front radius wall x 2 | 20 | 1
1 | 1040 | Roof Truss Setup Time | 15 | 1
1 | 1050 | Weld roof trusses (2 min ea) | 30 | 1
1 | 1060 | Weld roof parts together | 60 | 1
1 | 1070 | Table prep for 1 pc roof | 8 | 1
1 | 1080 | Roof lay out | 15 | 1
1 | 1090 | Tack roof | 8 | 2
1 | 1100 | Weld 1 pc roof | 20 | 2
1 | 1110 | A/C Ducting - Single | 10 | 2
1 | 1130 | Upper front wall | 30 | 1
1 | 1140 | Lower front wall | 15 | 1
1 | 1150 | Prep Table | 10 | 1
1 | 1160 | Rear wall header | 20 | 1
1 | 1170 | Lay Out C/S Sidewall | 65 | 2
1 | 1240 | Dinette CS - Front | 3 | 1
1 | 1280 | tack C/S sidewall | 50 | 2
1 | 1290 | weld C/S sidewall | 60 | 2
1 | 1310 | Grind; tape; flip; weld; grind C/S sidewall | 24 | 2
1 | 1320 | Lay Out R/S Sidewall | 90 | 2
1 | 1370 | Sofa - RS - Rear | 3 | 1
1 | 1410 | tack R/S sidewall | 20 | 2
1 | 1420 | weld R/S sidewall | 60 | 2
1 | 1440 | Grind; tape; flip; weld; grind R/S sidewall | 24 | 2
1 | 1450 | prep table | 15 | 2
1 | 1460 | Lay Out Frame | 65 | 2
1 | 1470 | Airline Track | 5 | 1
1 | 1480 | Tack Frame | 60 | 2
1 | 1490 | Weld frame | 80 | 2
1 | 1500 | 4in Addition Ht Sub Frame | 10 | 1
1 | 1510 | Tongue Tray - STD | 7 | 1
1 | 1530 | Drill Weep Holes | 10 | 1
1 | 1540 | Fresh tank | 25 | 1
1 | 1550 | Waste tanks | 15 | 1
1 | 1570 | Tank wiring and plumbing hook up | 70 | 1
1 | 1580 | 3 Season Plumbing | 20 | 1
1 | 1590 | Set Axles | 20 | 1
1 | 1600 | Brake wires | 20 | 1
1 | 1610 | Stamp VIN on Frame | 3 | 1
1 | 1640 | Install wheels | 15 | 1
1 | 1650 | Install Jacks; Sewer Hose; Spare Tire Rack; sewage hose holder | 25 | 1
1 | 1660 | Fasten Water Line | 35 | 1
1 | 1670 | Fresh Water Fill and Vent Hoses | 5 | 1

## ST4 Input
Station | Process_# | Process_Name | 8.5x20
4 | 4010 | Finish Water Heater | 10
4 | 4020 | Outside Water Fill | 6
4 | 4040 | LP Tray and Tanks | 7
4 | 4050 | install intellipower | 120
4 | 4060 | install battery disconnect & divider panal | 20
3 | 4080 | Interior Hook Up | 120
4 | 4100 | Trim Exterior Metal for Wheel Wells (8.5' wide only) | 15
4 | 4110 | Install LP Lines | 30
4 | 4120 | Main Switch Panel Hook Up No Stereo 45 | 45
4 | ***4130*** | 3 Season Plumbing | 5
4 | 4160 | Lower Rub Rail | 40
4 | ***4170*** | Cut Fenders to Proper Length and Front Trim - 8.5 Wide | 10
4 | 4180 | Wire Lower Clearance Lights | 15
4 | 4200 | Flow Through Vents | 20
4 | 4220 | Install Motorbase | 15
4 | 4240 | Install Outside Coax | 15
4 | 4260 | Exterior Recept Install | 15
4 | 4280 | Exterior 12V Outlet | 10
4 | 4300 | Install Kitchen Overhead | 17
4 | 4310 | Set Refer | 30
4 | 4320 | "Tail Lights | 60
4 | 4340 | Refer Hook Up | 14
4 | 4350 | Outside Refer Vent | 5
4 | 4360 | Outside Water Heater and Furnace Vent | 15
4 | 4380 | Install Outside Water Heater Door | 5
4 | 4390 | wire upper clearance lights | 35
4 | ***4400*** | Wire Loading Lights | 2
4 | 4410 | Trim Ramp Door Opening | 20
4 | 4420 | Install Windows (All Std) | 30
4 | 4450 | Day and Night Shades | 20
4 | 4460 | ATP Kickplate | 45
4 | ***4470*** | Hook Up A/C (1st) | 31
4 | 4490 | Cove | 120
4 | 4500 | Trim Interior | 60
4 | 4520 | Vents Garnish - Roof | 5
4 | 4580 | Towel Bar | 8
4 | 4590 | Install Mirror | 5
4 | 4600 | Shower Curtain Rod | 5
4 | 4610 | Install Toilet | 7
4 | 4620 | "LP Test | 25
4 | 4650 | Install Entrance Door | 7
4 | 4670 | Grab Handle Entrance Door | 5
4 | 4680 | Trim Entrance Door | 20
4 | 4690 | Refer Panels | 5
4 | 4700 | Awning cradle | 5
4 | 4710 | Awning | 30
4 | 4720 | Front Baggage Door | 10
4 | 4730 | Bathdoor | 10
4 | 4740 | Trim Bathroom Door | 15
4 | ***4850*** | Install Sofa - RS - Rear | 30
4 | ***4860*** | Install Dinette CS - Front | 45
4 | ***4910*** | Install Vinyl Zippered Rear Opening | 20
4 | 4920 | Flood Test | 80
4 | 4970 | install & hook up LP tanks | 15

## ST1 Input
Station | Process_# | Process_Name | 8.5x20 | People
5 | 5010 | Set Generator | 20 |  | SR
5 | 5020 | Generator cover prep | 37 |  | SR
5 | 5030 | cover install | 21 |  | SR
5 | 5040 | Wire in generator to transfer switch | 18 |  | SR
5 | 5050 | Generator test | 8 |  | SR
5 | 5060 | Ramp Door Install | 30 |  | NT
5 | 5080 | License Plate | 2
5 | 5090 | Grab Handles (Ramp) | 10 |  | NT
5 | 5100 | "Fire Ext. | 15 | 15 | NT
5 | 5110 | Clean Exterior | 35 |  | RW
5 | 5120 | Exterior Stickers and Logos | 20 |  | RW
5 | 5130 | Caulk Exterior | 40 |  | RW
5 | 5140 | Clean Interior | 70 |  | RW
5 | ***5280*** | Sofa - RS - Rear | 5 |  | RW
5 | ***5290*** | Dinette CS - Front | 5
5 | ***5340*** | Insulation - floor | 10
5 | 5350 | Interior Stickers | 11
5 | 5360 | Caulk Interior | 60
5 | 5370 | Shower Curtain | 5
5 | 5380 | Grease Caps | 2
5 | 5390 | Tighten Wheel Lugs & check air presure in tires | 5
5 | ***5400*** | Install Graphics | 120
5 | 5440 | Tie Down Rings | 2
5 | 5450 | Hi-Pot Test | 10
5 | 5460 | Electrical Systems check | 45
5 | 5470 | functionallity test | 20
5 | ***5560*** | Sofa - RS - Rear | 5
5 | ***5570*** | Dinette CS - Front | 5
5 | ***5660*** | Vinyl Rear Opening | 5