## Sheet1
[5 empty] | Shift Start | 5:00 |  | 0.20833
[5 empty] | Shift End | 13:15 |  | 0.55208
|  | VIN: |  |  | Start Time | 2016-11-07 10:45
[5 empty] | Number of People | 2
[5 empty] | TAKT | 1.75
Station | Process_# | Process_Name | 8.5x20 | People | Respoinsible |  | Heath | [9 empty] | Leon
1 | ***10*** | Weld interior walls -Std Unit |  | 1 |  | 42681.4479 | 1 | 42681.4479 | 42681.4479 | 1 | 1 | 1 | 42681.4479 |  |  |  |  | 42681.4479 | BAD | 0.44792
1 | 30 | Weld front radius wall x 2 | 20 | 1 | Heath | 42681.4618 | 1 | 42681.4618 | 42701.4479 | 1 | 1 | 1 | 42681.4618 |  |  |  |  | 42681.4479 |  | 0.46181
1 | 40 | Roof Truss Setup Time | 15 | 1 |  | 42681.4722 | 1 | 42681.4722 | 42716.4479 | 1 | 1 | 1 | 42681.4722 |  |  |  |  | 42681.4479 |  | 0.47222
1 | 50 | Weld roof trusses (2 min ea) | 30 | 1 |  | 42681.4931 | 1 | 42681.4931 | 42746.4479 | 1 | 1 | 1 | 42681.4931 |  |  |  |  | 42681.4479 |  | 0.49306
1 | 60 | Weld roof parts together | 60 | 1 |  | 42681.5347 | 1 | 42681.5347 | 42806.4479 | 1 | 1 | 1 | 42681.5347 |  |  |  |  | 42681.4479 |  | 0.53472
1 | 70 | Table prep for 1 pc roof | 8 | 1 | Heath | 42681.5403 | 1 | 42681.5403 | 42814.4479 | 1 | 1 | 1 | 42681.5403 |  |  |  |  | 42681.4479 |  | 0.54028
1 | 80 | Roof lay out | 15 | 1 | Heath | 42681.5507 | 1 | 42681.5507 | 42829.4479 | 1 | 1 | 1 | 42681.5507 |  |  |  |  | 42681.4479 |  | 0.55069
1 | 90 | Tack roof | 8 | 2 | Heath;Leon | 42681.5563 |  | 42681.5507 | 42829.4479 | 0 | 1 | 0 | 42681.5507 | 5:06 | 0.55208 | -0.33958 | 1 | 42681.5563 |  | 0.55069
1 | 100 | Weld 1 pc roof | 20 | 2 | Heath;Leon | 42681.5701 |  | 42681.5507 | 42829.4479 | 0 | 1 | 0 | 42681.5507 |  |  |  | 1 | 42681.5646 |  | 0.55069
1 | ***110*** | A/C Ducting - Single | 10 | 2 | Heath;Leon | 42681.5771 |  | 42681.5507 | 42829.4479 | 0 | 1 | 0 | 42681.5507 |  |  |  | 1 | 42681.5576 |  | 0.55069
1 | 130 | Upper front wall | 30 | 1 |  | 42681.5979 |  | 42681.5507 | 42829.4479 | 0 | 1 | 0 | 42681.5507 |  |  |  | 1 | 42681.5715 |  | 0.55069
1 | 140 | Lower front wall | 15 | 1 |  | 42681.6083 |  | 42681.5507 | 42829.4479 | 0 | 1 | 0 | 42681.5507 |  |  |  | 1 | 42681.5611 |  | 0.55069
1 | 150 | Prep Table | 10 | 1 |  | 42681.6153 |  | 42681.5507 | 42829.4479 | 0 | 1 | 0 | 42681.5507 |  |  |  | 1 | 42681.5576 |  | 0.55069
1 | 160 | Rear wall header | 20 | 1 |  | 42681.6292 |  | 42681.5507 | 42829.4479 | 0 | 1 | 0 | 42681.5507 |  |  |  | 1 | 42681.5646 |  | 0.55069
1 | 170 | Lay Out C/S Sidewall | 65 | 2 | Heath;Leon | 42681.6743 |  | 42681.5507 | 42829.4479 | 0 | 1 | 0 | 42681.5507 |  |  |  | 1 | 42681.5958 |  | 0.55069
1 | ***240*** | Dinette CS - Front | 3 | 1 |  | 42681.6764 |  | 42681.5507 | 42829.4479 | 0 | 1 | 0 | 42681.5507 |  |  |  | 1 | 42681.5528 |  | 0.55069
1 | 280 | tack C/S sidewall | 50 | 2 | Heath;Leon | 42681.7111 | 1 | 5:48 | 42879.4479 | 1 | 1 | 0 | 5:48 |  |  |  |  | 42681.5528 |  | 0.24167
1 | 290 | weld C/S sidewall | 60 | 2 | Heath;Leon | 42681.7528 | 1 | 6:48 | 42939.4479 | 1 | 1 | 1 | 6:48 |  |  |  |  | 42681.5528 |  | 0.28333
1 | 310 | Grind; tape; flip; weld; grind C/S sidewall | 24 | 2 | Heath;Leon | 42681.7694 | 1 | 7:12 | 42963.4479 | 1 | 1 | 1 | 7:12 |  |  |  |  | 42681.5528 |  | 0.3
1 | 320 | Lay Out R/S Sidewall | 90 | 2 | Heath;Leon | 42681.8319 | 1 | 8:42 | 43053.4479 | 1 | 1 | 1 | 8:42 |  |  |  |  | 42681.5528 |  | 0.3625
1 | ***370*** | Sofa - RS - Rear | 3 | 1 |  | 42681.834 | 1 | 8:45 | 43056.4479 |  |  |  | 8:45 |  |  |  |  | 42681.5528 |  | 0.36458
1 | 410 | tack R/S sidewall | 20 | 2 | Heath;Leon | 42681.8479 | 1 | 9:05 | 43076.4479 | [8 empty] | 42681.5528 |  | 0.37847
1 | 420 | weld R/S sidewall | 60 | 2 | Heath;Leon | 42681.8896 |  | 9:05 | 43076.4479 | [8 empty] | 42681.5528 |  | 0.37847
1 | 430 | Grind; tape; flip; weld; grind R/S sidewall | 24 | 2 | Heath;Leon | 42681.9063 |  | 9:05 | [9 empty] | 42681.5528
1 | 440 | prep table | 15 | 2 | Heath;Leon | 42681.9167 |  | 9:05 | [9 empty] | 42681.5528
1 | 450 | Lay Out Frame | 100 | 2 | Heath;Leon | 42681.9861 |  | 9:05 | [9 empty] | 42681.5528
1 | 460 | Tack Frame | 60 | 2 | Heath;Leon | 42682.0278 |  | 9:05 | [9 empty] | 42681.5528
1 | 470 | Weld frame | 80 | 2 | Heath;Leon | 42682.0833 |  | 9:05 | [9 empty] | 42681.5528
1 | ***470*** | 4in Addition Ht Sub Frame | 10 | 1 |  | 42682.0903 | 1 | 9:15 | [9 empty] | 42681.5528
1 | ***470*** | Tongue Tray - STD | 7 | 1 |  | 42682.0951 | 1 | 9:22 | [9 empty] | 42681.5528
1 | 480 | Drill Weep Holes | 10 | 1 |  | 42682.1021 | 1 | 9:32 | [9 empty] | 42681.5528
1 | 490 | Fresh tank | 25 | 1 |  | 42682.1194 | 1 | 9:57 | [9 empty] | 42681.5528
1 | 500 | Waste tanks | 15 | 1 |  | 42682.1299 | 1 | 10:12 | [9 empty] | 42681.5528
1 | 520 | Tank wiring and plumbing hook up | 70 | 1 |  | 42682.1785 |  | 10:12 | [9 empty] | 42681.5528
1 | ***530*** | 3 Season Plumbing | 20 | 1 |  | 42682.1924 |  | 10:12 | [9 empty] | 42681.5528
1 | 540 | Set Axles | 20 | 1 |  | 42682.2063 |  | 10:12 | [9 empty] | 42681.5528
1 | 550 | Brake wires | 20 | 1 |  | 42682.2201 |  | 10:12 | [9 empty] | 42681.5528
1 | 560 | Stamp VIN on Frame | 3 | 1 |  | 42682.2222 |  | 10:12 | [9 empty] | 42681.5528
1 | 590 | Install wheels | 15 | 1 |  | 42682.2326 |  | 10:12 | [9 empty] | 42681.5528
1 | 600 | Install Jacks; Sewer Hose; Spare Tire Rack; sewage hose holder | 25 | 1 |  | 42682.25 |  | 10:12 | [9 empty] | 42681.5528
1 | 610 | Fasten Water Line | 35 | 1 |  | 42682.2743 |  | 10:12 | [9 empty] | 42681.5528
1 | 620 | Fresh Water Fill and Vent Hoses | 5 | 1 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
0 | 0 | 0 | 0 | 0 |  | 42682.2778 |  | 10:12 | [9 empty] | 42681.5528
1195
19.9167

## 206050 - Earth MotorCars - Stoc
Station | Process_# | Process_Name | 8.5x20 | People | Respoinsible
1 | ***10*** | Weld interior walls -Std Unit | 270 | 1
1 | 30 | Weld front radius wall x 2 | 20 | 1 | Heath
1 | 40 | Roof Truss Setup Time | 15 | 1
1 | 50 | Weld roof trusses (2 min ea) | 30 | 1
1 | 60 | Weld roof parts together | 60 | 1
1 | 70 | Table prep for 1 pc roof | 8 | 1 | Heath
1 | 80 | Roof lay out | 15 | 1 | Heath
1 | 90 | Tack roof | 8 | 2 | Heath;Leon
1 | 100 | Weld 1 pc roof | 20 | 2 | Heath;Leon
1 | ***110*** | A/C Ducting - Single | 10 | 2 | Heath;Leon
1 | 130 | Upper front wall | 30 | 1
1 | 140 | Lower front wall | 15 | 1
1 | 150 | Prep Table | 10 | 1
1 | 160 | Rear wall header | 20 | 1
1 | 170 | Lay Out C/S Sidewall | 65 | 2 | Heath;Leon
1 | ***240*** | Dinette CS - Front | 3 | 1
1 | 280 | tack C/S sidewall | 50 | 2 | Heath;Leon
1 | 290 | weld C/S sidewall | 60 | 2 | Heath;Leon
1 | 310 | Grind; tape; flip; weld; grind C/S sidewall | 24 | 2 | Heath;Leon
1 | 320 | Lay Out R/S Sidewall | 90 | 2 | Heath;Leon
1 | ***370*** | Sofa - RS - Rear | 3 | 1
1 | 410 | tack R/S sidewall | 20 | 2 | Heath;Leon
1 | 420 | weld R/S sidewall | 60 | 2 | Heath;Leon
1 | 430 | Grind; tape; flip; weld; grind R/S sidewall | 24 | 2 | Heath;Leon
1 | 440 | prep table | 15 | 2 | Heath;Leon
1 | 450 | Lay Out Frame | 100 | 2 | Heath;Leon
1 | 460 | Tack Frame | 60 | 2 | Heath;Leon
1 | 470 | Weld frame | 80 | 2 | Heath;Leon
1 | ***470*** | 4in Addition Ht Sub Frame | 10 | 1
1 | ***470*** | Tongue Tray - STD | 7 | 1
1 | 480 | Drill Weep Holes | 10 | 1
1 | 490 | Fresh tank | 25 | 1
1 | 500 | Waste tanks | 15 | 1
1 | 520 | Tank wiring and plumbing hook up | 70 | 1
1 | ***530*** | 3 Season Plumbing | 20 | 1
1 | 540 | Set Axles | 20 | 1
1 | 550 | Brake wires | 20 | 1
1 | 560 | Stamp VIN on Frame | 3 | 1
1 | 590 | Install wheels | 15 | 1
1 | 600 | Install Jacks; Sewer Hose; Spare Tire Rack; sewage hose holder | 25 | 1
1 | 610 | Fasten Water Line | 35 | 1
1 | 620 | Fresh Water Fill and Vent Hoses | 5 | 1
1465
24.4167