## Sheet1
|  | Shift Start | 5:05
|  | Break Start Time | 8:50
|  | Break End Time | 9:05
|  | Shift End | 13:05
|  | Start Time | 2016-11-07 10:45
End Time
|  | Number of People | 2
|  | TAKT | 1.75 | DAYS
|  | Minutes per TAKT | 1627.5 | 813.75
|  | Predicted Schedule Time | 1195
|  | Available Time | 432.5
|  | Actual Scheduled Time | 447
Station | Process_# | Process_Name | 8.5x20 | People | Comments / Issues | Heath |  |  |  | Leon |  |  |  | Check
1 | ***10*** | Weld interior walls -Std Unit | 0 | 1 |  |  | 42681.4479 | 0 | 1627.5 | 1 | 42681.4479 | 0 | 1627.5 | TRUE
1 | 30 | Weld front radius wall x 2 | 20 | 1 |  | 1 | 42681.4618 | 20 | 1607.5 |  | 42681.4479 | 0 | 1607.5 | TRUE
1 | 40 | Roof Truss Setup Time | 15 | 1 |  | 1 | 42681.4722 | 35 | 1592.5 | 1 | 42681.4583 | 15 | 1592.5 | TRUE
1 | 50 | Weld roof trusses (2 min ea) | 30 | 1 |  | 1 | 42681.4931 | 65 | 1562.5 | 1 | 42681.4792 | 45 | 1562.5 | TRUE
1 | 60 | Weld roof parts together | 60 | 1 |  | 1 | 42681.5347 | 125 | 1502.5 |  | 42681.4792 | 45 | 1502.5 | TRUE
1 | 70 | Grind; tape; flip; weld; grind C/S sidewall | 24 | 1 |  |  | 42681.5347 | 125 | 1502.5 | 1 | 42681.4958 | 69 | 1502.5 | TRUE
1 | 80 | Roof lay out | 15 | 1 |  |  | 42681.5347 | 125 | 1502.5 | 1 | 42681.5062 | 84 | 1502.5 | TRUE
1 | 90 | Tack roof | 8 | 2 |  |  | 42681.5347 | 125 | 1502.5 | 1 | 42681.5118 | 92 | 1502.5 | TRUE
1 | 100 | Weld 1 pc roof | 20 | 2 |  |  | 42681.5347 | 125 | 1502.5 | 1 | 42681.5257 | 112 | 1502.5 | TRUE
1 | ***110*** | A/C Ducting - Single | 10 | 2 |  |  | 42681.5347 | 125 | 1502.5 | 1 | 42681.5326 | 122 | 1502.5 | TRUE
1 | 130 | Upper front wall | 30 | 1 |  |  | 42681.5347 | 125 | 1502.5 |  | 42681.5326 | 122 | 1502.5 | FALSE
1 | 140 | Lower front wall | 15 | 1 |  |  | 42681.5347 | 125 | 1502.5 |  | 42681.5326 | 122 | 1502.5 | FALSE
1 | 150 | Prep Table | 10 | 1 |  |  | 42681.5347 | 125 | 1502.5 |  | 42681.5326 | 122 | 1502.5 | FALSE
1 | 160 | Rear wall header | 20 | 1 |  |  | 42681.5347 | 125 | 1502.5 |  | 42681.5326 | 122 | 1502.5 | FALSE
1 | 170 | Lay Out C/S Sidewall | 65 | 2 |  |  | 42681.5347 | 125 | 1502.5 |  | 42681.5326 | 122 | 1502.5 | FALSE
1 | ***240*** | Dinette CS - Front | 3 | 1 |  |  | 42681.5347 | 125 | 1502.5 |  | 42681.5326 | 122 | 1502.5 | FALSE
1 | 280 | tack C/S sidewall | 50 | 2 |  | 1 | 5:40 | 175 | 1452.5 |  | 42681.5326 | 122 | 1452.5 | TRUE
1 | 290 | weld C/S sidewall | 60 | 2 |  |  | 5:40 | 175 | 1452.5 |  | 42681.5326 | 122 | 1452.5 | FALSE
1 | 310 | Table prep for 1 pc roof | 8 | 2 |  |  | 5:40 | 175 | 1452.5 |  | 42681.5326 | 122 | 1452.5 | FALSE
1 | 320 | Lay Out R/S Sidewall | 90 | 2 |  | 1 | 7:10 | 265 | 1362.5 |  | 42681.5326 | 122 | 1362.5 | TRUE
1 | ***370*** | Sofa - RS - Rear | 3 | 1 |  |  | 7:10 | 265 | 1362.5 |  | 42681.5326 | 122 | 1362.5 | FALSE
1 | 410 | tack R/S sidewall | 20 | 2 |  |  | 7:10 | 265 | 1362.5 |  | 42681.5326 | 122 | 1362.5 | FALSE
1 | 420 | weld R/S sidewall | 60 | 2 |  | 1 | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | TRUE
1 | 430 | Grind; tape; flip; weld; grind R/S sidewall | 24 | 2 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 440 | prep table | 15 | 2 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 450 | Lay Out Frame | 100 | 2 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 460 | Tack Frame | 60 | 2 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 470 | Weld frame | 80 | 2 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | ***470*** | 4in Addition Ht Sub Frame | 10 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | ***470*** | Tongue Tray - STD | 7 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 480 | Drill Weep Holes | 10 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 490 | Fresh tank | 25 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 500 | Waste tanks | 15 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 520 | Tank wiring and plumbing hook up | 70 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | ***530*** | 3 Season Plumbing | 20 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 540 | Set Axles | 20 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 550 | Brake wires | 20 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 560 | Stamp VIN on Frame | 3 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 590 | Install wheels | 15 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 600 | Install Jacks; Sewer Hose; Spare Tire Rack; sewage hose holder | 25 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 610 | Fasten Water Line | 35 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
1 | 620 | Fresh Water Fill and Vent Hoses | 5 | 1 |  |  | 8:10 | 325 | 1302.5 |  | 42681.5326 | 122 | 1302.5 | FALSE
19.9167

## 206050 - Earth MotorCars - Stoc
Station | Process_# | Process_Name | 8.5x20 | People | Respoinsible
1 | ***10*** | Weld interior walls -Std Unit | 270 | 1
1 | 30 | Weld front radius wall x 2 | 20 | 1 | Heath
1 | 40 | Roof Truss Setup Time | 15 | 1
1 | 50 | Weld roof trusses (2 min ea) | 30 | 1
1 | 60 | Weld roof parts together | 60 | 1
1 | 70 | Grind; tape; flip; weld; grind C/S sidewall | 24 | 1 | Heath
1 | 80 | Roof lay out | 15 | 1 | Heath
1 | 90 | Tack roof | 8 | 2 | Heath;Leon
1 | 100 | Weld 1 pc roof | 20 | 2 | Heath;Leon
1 | ***110*** | A/C Ducting - Single | 10 | 2 | Heath;Leon
1 | 130 | Upper front wall | 30 | 1
1 | 140 | Lower front wall | 15 | 1
1 | 150 | Prep Table | 10 | 1
1 | 160 | Rear wall header | 20 | 1
1 | 170 | Lay Out C/S Sidewall | 65 | 2 | Heath;Leon
1 | ***240*** | Dinette CS - Front | 3 | 1
1 | 280 | tack C/S sidewall | 50 | 2 | Heath;Leon
1 | 290 | weld C/S sidewall | 60 | 2 | Heath;Leon
1 | 310 | Table prep for 1 pc roof | 8 | 2 | Heath;Leon
1 | 320 | Lay Out R/S Sidewall | 90 | 2 | Heath;Leon
1 | ***370*** | Sofa - RS - Rear | 3 | 1
1 | 410 | tack R/S sidewall | 20 | 2 | Heath;Leon
1 | 420 | weld R/S sidewall | 60 | 2 | Heath;Leon
1 | 430 | Grind; tape; flip; weld; grind R/S sidewall | 24 | 2 | Heath;Leon
1 | 440 | prep table | 15 | 2 | Heath;Leon
1 | 450 | Lay Out Frame | 100 | 2 | Heath;Leon
1 | 460 | Tack Frame | 60 | 2 | Heath;Leon
1 | 470 | Weld frame | 80 | 2 | Heath;Leon
1 | ***470*** | 4in Addition Ht Sub Frame | 10 | 1
1 | ***470*** | Tongue Tray - STD | 7 | 1
1 | 480 | Drill Weep Holes | 10 | 1
1 | 490 | Fresh tank | 25 | 1
1 | 500 | Waste tanks | 15 | 1
1 | 520 | Tank wiring and plumbing hook up | 70 | 1
1 | ***530*** | 3 Season Plumbing | 20 | 1
1 | 540 | Set Axles | 20 | 1
1 | 550 | Brake wires | 20 | 1
1 | 560 | Stamp VIN on Frame | 3 | 1
1 | 590 | Install wheels | 15 | 1
1 | 600 | Install Jacks; Sewer Hose; Spare Tire Rack; sewage hose holder | 25 | 1
1 | 610 | Fasten Water Line | 35 | 1
1 | 620 | Fresh Water Fill and Vent Hoses | 5 | 1
1465
24.4167